## Cover Page
The following tabs are found in this document:
1. Page Elements | 7. Returns
2. Landing Page | 8. Receive Orders & Transfers
3. Approve Orders | 9. Cold Storage
4. Create Orders | 10. Search History
5. Reconciliation | 11. Search/Add Inventory
6. Transfers | 12. Admin & Settings
The following tabs are found in this document:
  1. Cover Page 7. Onboarding Panel
  2. Page Elements 8. Transacton Log Viewer
  3. Single Sign-On 9. Action Items
  4. Landing Page 10. DQA 5. Admin 11. Data Summary
  6. Provider 12. Trends (State)
  13. Trends (OC/FC)
v. April 2018
STC|iQ

## Page Elements
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
State logo image (State Logo Placeholder) & STC Logo | 1. Confirm the presence of your State's logo image above the log-in and STC logo at the bottom of the screen |  | RC |  |  |  | Ousswa | RC
|  |  | OC |  |  |  | Ousswa | OC
|  |  | FC |  |  |  | Ousswa | FC
Log in | 1. Login to your state's environment for iQ using your assigned username and password. 2. Select Login 3. Confirm that you have been logged into the system |  | RC |  |  |  |  | RC
|  |  | OC |  |  |  |  | OC
|  |  | FC |  |  |  |  | FC
Forgot Password (if enabled) ***Due to an email being required for every user, only one type of account can be used for testing unless two other email accounts are used*** | 1. On your state's login page, select "Forgot Password?" 2. Enter your username or email address in the text box and click Submit. 3. Confirm that a text box appears "You should Receive an email shortly with further instructions." 4. Confirm receiving the email and the link allows you to reset your password. |  | RC |  |  |  |  | RC
Search bar is prepopulated with organization and facility | 1. When logged into the system, confirm that the search bar is prepopulated with an organization and facility. 2. Confirm that you cannot change the organization or facility. |  | FC |  |  |  |  | FC
Search bar is prepopulated with organization | 1. When logged into the system, confirm that the search bar is prepopulated with an organization. 2. Confirm that the organization cannot be changed in the search bar. 3. Confirm that you can search for a facility by name or IIS ID. |  | OC |  |  |  |  | OC
Search bar for RC users | 1. Confirm that the search bar is empty and user can search for any organization and facility. 2. Confirm that user can search by name or IIS ID. |  | RC |  |  |  |  | RC
Elements display as expected All links function as expected | 1. Confirm the presence of iQ logo. 2. Confirm the presence of the search bar. 3. Confirm the presence of the Healthcare Provider Onboarding panel (two feet) and when selected a panel slides in from the right with provider information 4. Confirm the presence of Alerts (bell) and when selected a panel opens with alerts 5. Confirm that the "i" Icon is present and opens a new tab to the User Guide when selected. 6. Confirm the presence of the foursquare button. a. Confirm that selecting the foursquare results in icons for other applications b. Confirm that each existing icon brings you to the application successfully. 7. Confirm the presence of the Log Out icon and when selected you are logged out of the system. |  | RC |  |  |  |  | RC
| 1. Confirm the presence of iQ logo. 2. Confirm the presence of the search bar. 3. Confirm the presence of Alerts (bell) and when selected a panel opens with alerts 4. Confirm that the "i" Icon is present and opens a new tab to the User Guide when selected. 5. Confirm the presence of the foursquare button. a. Confirm that selecting the foursquare results in icons for other applications b. Confirm that each existing icon brings you to the application successfully. 6. Confirm the presence of the Log Out icon and when selected you are logged out of the system. |  | OC |  |  |  |  | OC
| 1. Confirm the presence of iQ logo. 2. Confirm the presence of the search bar. 3. Confirm the presence of Alerts (bell) and when selected a panel opens with alerts 4. Confirm that the "i" Icon is present and opens a new tab to the User Guide when selected. 5. Confirm the presence of the foursquare button. a. Confirm that selecting the foursquare results in icons for other applications b. Confirm that each existing icon brings you to the application successfully. 6. Confirm the presence of the Log Out icon and when selected you are logged out of the system. |  | FC |  |  |  |  | FC

## Single-Sign-On
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
Test 1 | 1. Login as a User that also has access to PHC-Hub, iQ, and iWeb 2. On the Dashboard, select PHC-Hub and ensure the user is not required to log in again to use the application 3. Select a different Organization and click Submit 4. Verify the message, "Unable to login, please select correct provider" appears 5. Select the correct organization and click Submit 6. Select Main > Application Dashboard 7. Click on iWeb and ensure the user is not required to log in again to use the application 8. Logout and close and re-open the browser 9. Login and select iWeb from the Dashboard 10. Ensure the user is logged in and select Dashboard from the left menu 11. Select PHC-Hub and ensure the user is not required to log in again to use the application 12. Select the correct organization and click Submit 13. Select Main > Application Dashboard 14. Select iQ and ensure the user is not required to log in again to use the application 15. Logout (upper right hand corner the "Person" icon) 16. Verify you are taken back to the SSO login page |  | OC |  |  |  |  | OC
|  |  | FC |  |  |  |  | FC
Test 3 | 1. Login to the STC Dashboard as a User that has access to iQ 2. Ensure the user is logged in then select iQ and ensure the user is able to use iQ with the correct access 3. Return to the STC Dashboard and ensure the user is still logged in |  | OC |  |  |  |  | OC
|  |  | FC |  |  |  |  | FC
Test 4 | 1. Login to iQ as any User with access to iQ 2. Remain inactive for up to 30 minutes 3. Ensure the user is logged out due to inactivity and the user is returned to the SSO login page |  | OC |  |  |  |  | OC
|  |  | FC |  |  |  |  | FC

## Landing Page
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
Display Healthcare Provider Count by Onboarding Stages | 1. Navigate to Provider List and count the number of providers under each stage 2. Verify all stages are listed along with the correct number of providers |  | RC |  |  |  |  | RC
Display at Each Milestone | 1. Verify 'X' displays under each milestone, such as HL7 Validation, Issue Resolution Validation, Processing in the IIS, and Saved in IIS. |  | RC |  |  |  |  | RC
Display Onboarding Healthcare Provider Counts by HL7 Version | 1. Verify 'X' displays under 2.3.1 and 2.5.1 |  | RC |  |  |  |  | RC
Display Onboarding Healthcare Provider Counts by MU Stages | 1. Verify 'X' displays under Meaningful Stage 1, 2, & 3 |  | RC |  |  |  |  | RC
Display HL7 Message Success Tracker | 1. Log in as an OC user 2. Verify the success rate is calculated correctly by dividing the Total Number of Messages Submitted (including Failed messages) into the number of Successful Messages. |  | OC |  |  |  |  | OC
| 1. Log in as an FC user 2. Verify the success rate is calculated correctly by dividing the Total Number of Messages Submitted (including Failed messages) into the number of Successful Messages. |  | FC |  |  |  |  | FC
Display Record Errors Received by PHC-Hub | 1. Log in as an OC user 2. Verify the number of Errors are based on Vaccination Data Elements and Patient Data Elements flagged by the Issue Resolutions. |  | OC |  |  |  |  | OC
| 1. Log in as an FC user 2. Verify the number of Errors are based on Vaccination Data Elements and Patient Data Elements flagged by the Issue Resolutions |  | FC |  |  |  |  | FC
Display Top 5 Record Errors | 1. Log in as an OC user 2. Verify the five most common data errors are shown |  | OC |  |  |  |  | OC
| 1. Log in as an OC user 2. Verify the five most common data errors are shown |  | FC |  |  |  |  | FC
DisplayTop 5 Record Warnings | 1. Log in as an OC user 2. Verify the five most common data warnings are shown |  | OC |  |  |  |  | OC
| 1. Log in as an FC user 2. Verify the five most common data warnings are shown |  | FC |  |  |  |  | FC

## Admin
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
DQA
Add/Edit State Expectation Rates & Issue Resolution Recommendations (Use Import Profile Core Testing Issue Resolutions 6.15.18 for Step 6) | 1. Login to iQ as a State User 2. Select Admin and click on DQA 3. Confirm Data Quality Assessment Tool is visible with these sections: a. Guardian Information b. History Information c. Patient Information d. Patient Next of Kin Information e. Patient Vaccination Information 4. Click on down arrow (expand) of each of the sections listed above. 5. Verify that four columns are visible and editable (except for Edit): a. HL7 Data Element b. HL7 Code c. State Expectation Rate d. Edit 6. Verify the HL7 Data Elements under each section match the Issue Resolutions in PHC Hub 7. Click on 'pencil' under Edit column for each HL7 Data Element to verify that the following fields are visible: a. Data Element Name - verify this is NOT editable b. State Expectation Rate - verify this is editable c. Recommendations - verify that the issues listed match the issues available under that Data Element Name in a PHC Hub import profile. 8. Enter State Expectation Rate (for one enter a '0' and Recommendations for a HL7 Data Element. 9. Click Submit and verify the addition was made 10. Click on the 'Edit' icon and make a change. 11. Click Submit and verify the changes were made. 12. Complete steps 7 thru 10 for at least 5 HL7 Data Elements under each section. |  | RC |  |  |  |  | RC
Alerts
NOT WORKING AT THIS TIME
Onboarding
Select Onboarding Stages | 1. Login to iQ as a State User 2. Select Onboarding > Onboarding Preferences 3. Expand Select Onboarding Stages 4. Verify that the following stages are unabled to be unchecked: a. Pre-Discovery b. Wait-Listed Ready c. Wait-Listed Not Ready d. Production 5. Check or uncheck the box beside the following stages: a. Discovery b. Planning c. Development d. Testing e. Pre-Go Live 6. Verify pop-up message of 'Stage Updated' or a pop-up of 'WARNING There are providers in this onboarding stage. Do you want to proceed?' 7. Click 'Continue' 8. Select Provider > Provider List 9. Verify the Discovery stage is no longer visible 10. Click the drop down under the Stage column and verify all stages are listed. |  | RC |  |  |  |  | RC
Activate/Deactivate Waitlist and Ranking | 1. Login to iQ as a State User 2. Select Onboarding > Onboarding Preferences 3. Expand Activate/Deactivate Waitlist and Ranking 4. Ensure the *Note statement has all words spelled correctly 4. Move toggle to On 5. Select Provider > Provider List 6. Verify Wait-Listed Ready and Wait-Listed Not Ready is visible 7. Select Onboarding > Onboarding Preferences 8. Expand Activate/Deactivate Waitlist and Ranking 9. Move toggle to Off 10. Select Provider > Provider List 11. Verify Wait-Listed Ready and Wait-Listed Not Ready are NOT visible |  | RC |  |  |  |  | RC
Create Organization Groups | 1. Login to iQ as a State User 2. Select Onboarding > Onboarding Preferences 3. Expand Create Organization Groups 4. Enter a group name on line beside '+' 5. Click on '+' 6. Verify group name is listed 7. Click on '-' to delete a group 8. Verify group was deleted |  | RC |  |  |  |  | RC
Standard Tasks | 1. Login to iQ as a State User 2. Select Onboarding > Onboarding Preferences 3. Expand Standard Tasks 4. Verify that the tasks listed are editable and can be checked or unchecked. 5. Uncheck a task and confirm pop-up message of 'Task status set' 6. Enter a State-Specific Task on line beside '+' 7. Click on '+' 8. Verify task is listed 9. Click on '-' to delete a task 10. Verify task was deleted |  | RC |  |  |  |  | RC
Email Settings | 1. Login to iQ as a State User 2. Select Onboarding > Onboarding Preferences 3. Expand Email Settings 4. Enter or change some information on template 5. Click Save Email Template 6. Confirm pop-up message of 'Template set' 7. Verify changes were made |  | RC |  |  |  |  | RC
Reports Logo
Upload logo | 1. Login to iQ as a State User 2. Select Admin > Reports Logo 3. Drag and drop a state logo in the box 4. Click Upload 5. Confirm pop-up message of 'Upload Successful' 6. Verify the logo displays below the box |  | RC |  |  |  |  | RC
Interface Form
Create Interface Form (if an Inferface Form has already been created, skip this test) | 1. Login to iQ as a State User 2. Select Onboarding > Interface Form 3. Click on 'Create New' 4. Verify a blank interface form appears with the following tabs: a. Provider Info b. EHR Info c. EHR Docs d. IIS Participation e. MU & Status f. Bi-Direction 5. Review each question to ensure correct grammar, spelling and punctuation 6. Drag and drop all components on the left to the interface form for each tab 7. Verify components have been added to form 8. Per tab, identify some components as required by checking 'Required' box 9. Per tab, identify some components as state only by checking 'State Only' box 10. Per tab, enter a tooltip on some components by clicking on 'Placeholder Tooltip Text' 11. Per tab, enter a score on some components by selecting 'Add score to option' drop down 12. Per tab, delete a component and verify it's added back to the list on the left 13. After deleting a component, click on 'x' to Cancel 14. Verify the component is not deleted 15. Click the Save icon (disk) 16. Verify form was saved under the Draft section |  | RC |  |  |  |  | RC
Edit Interface Form | 1. Login to iQ as a State User 2. Select Admin > Interface Form 3. Select the 'Edit' icon under the Draft section 4. Per tab make a few changes and click the 'Save' icon 5. Verify the updated form is listed under the Draft section with the form number increased by one, i.e. "6.1" |  | RC |  |  |  |  | RC
Publish Interface Form | 1. Login to iQ as a State User 2. Select Admin > Interface Form 3. Select the 'Publish' icon (up arrow) beside the top draft form under the Draft section 4. Verify pop-up message of 'WARNING This will become the new active form' 5. Select 'Cancel' and verify the form wasn't published 6. Select 'Publish' and click Continue 7. Verify the Form is moved to the Action Section with a new number, i.e. 7.0 8. Verify the old interface form is moved to the Archived section and an interface form is added to the Draft section with the same number as the Active one 9. To view the published form, click on the view icon (eye) 10. Click on the 'Cancel' icon and verify the interface form main screen is visisble 11. Select View again and click on the 'State' icon (state building) to view all questions 12. Select the 'Provider' icon (provider building) to hide the state only questions |  | RC |  |  |  |  | RC
View an Archived Form | 1. Login to iQ as a State User 2. Select Admin > Interface Form 3. Select the 'View' icon beside the top Archived form under the Archived section 4. Click on the 'Cancel' icon and verify the interface form main screen is visisble 5. Select View again and click on the 'State' icon (state building) to view all questions 6. Select the 'Provider' icon (provider building) to hide the state only questions |  | RC |  |  |  |  | RC
Global Contacts
Add a Contact | 1. Login to iQ as a State User 2. Select Admin > Global Contacts 3. In the Search box, start typing a name to add 4. If the person is not listed, click the 'Add' icon 5. Add the following information: a. First Name b. Last Name c. Position d. Phone e. Email 6. Click Cancel and verify the contact wasn't added, the search box is empty and the search screen list all contacts 7. Click on the Add icon 8. Add all the information except the Position 9. Click Create 10. Verify a message appears under Position that states, 'This field must not be blank' 11. Enter Position and click Create 12. Verify the contact was added to list and the search box is empty and the search screen list all contacts |  | RC |  |  |  |  | RC
Edit a Contact | 1. Login to iQ as a State User 2. Select Admin > Global Contacts 3. Click the 'Edit' icon beside any contact 4. Click 'Cancel' 5. Click the 'Edit' icon beside the same contact 6. Verify the contact's information is visible 7. Click the 'Edit' icon beside another contact 8. Make a change to the contact and click 'Cancel' 5. Verify the change wasn't saved and the contact's information is visible 6. Click on the 'Edit' icon beside another contact 7. Make a change to the contact and click 'Update' 8. Verify the change was made |  | RC |  |  |  |  | RC
Delete a Contact | 1. Login to iQ as a State User 2. Select Admin > Global Contacts 3. Click on the 'Delete' icon (trashcan) beside any contact 4. Verify pop-up message of 'WARNING Are you sure you want to delete this contact?' 5. Click 'Cancel' 6. Verify the contact wasn't deleted 7. Click on the 'Delete' icon (trashcan) beside any contact 8. Verify pop-up message of 'WARNING Are you sure you want to delete this contact?' 9. Click 'Continue' 10. Verify the contact was deleted |  | RC |  |  |  |  | RC
Send a email | 1. Login to iQ as a State User 2. Select Admin > Global Contacts 3. Check the box beside any contact 4. Verify a button stating 'Send Email' is visible at the bottom of the list 5. Click 'Send Email' 6. Verify a window is opened to compose and send an email with the contact in the 'To' field |  | RC |  |  |  |  | RC
Contact Groups
Create a Contact Group | 1. Login to iQ as a State User 2. Select Admin > Contact Groups 3. In the Search box, start typing a contact group name to add 4. If the group is not listed, click the 'Add' icon 5. Enter the List Name and Description 6. Verify that all contacts are visible to be selected 7. Select the contacts to be added to group by checking the box by each name. 8. Click Cancel and verify the group wasn't added and the search box is empty 9. Click on the Add icon 10. Verity the previous contacts checked aren't checked 11. Enter the List Name and Description 12. Select the contacts to be added to group by checking the box by each name. 13. Click Create and verify the group was created and the search box is empty 14. Click on the Add icon 15. Verify that no contacts are checked |  | RC |  |  |  |  | RC
View Contact Groups | 1. Login to iQ as a State User 2. Select Admin > Contact Groups 3. In the Search box, start typing a contact group name 4. When the group appears, click to 'Expand' 5. Verify the Description is visible and the contacts are listed 6. Verify the following icons are available: a. Delete (trashcan) b. Email (mail) c. Add contacts (person) d. Edit (pencil) e. Delete (X) beside each contact |  | RC |  |  |  |  | RC
Edit Contact Groups | 1. Login to iQ as a State User 2. Select Admin > Contact Groups 3. In the Search box, start typing a contact group name 4. When the group appears, click to 'Expand' 5. Select the 'Edit' icon and make a change 6. Click Cancel and verify the change wasn't made 7. Click on the 'Edit' icon 8. Edit the Description 9. Click 'Update' and verify the change was made |  | RC |  |  |  |  | RC
Send email to contact | 1. Login to iQ as a State User 2. Select Admin > Contact Groups 3. In the Search box, start typing a contact group name 4. When the group appears, click to 'Expand' 5. Select the 'Email' icon 6. Verify an email opens up with all the email addresses of contacts in group are listed in the 'To" field |  | RC |  |  |  |  | RC
Add more Contacts to Group | 1. Login to iQ as a State User 2. Select Admin > Contact Groups 3. In the Search box, start typing a contact group name 4. When the group appears, click to 'Expand' 5. Select the 'Add Contacts' icon 6. Select another contact to add to group 7. Click 'Cancel' and verify contact was not added to the group 8. Select the 'Add Contacts' icon 9. Select another contact to add to group 10. Click 'Add' and verify contact was added to the group |  | RC |  |  |  |  | RC
Delete Contact | 1. Login to iQ as a State User 2. Select Admin > Contact Groups 3. In the Search box, start typing a contact group name 4. When the group appears, click to 'Expand' 5. Select the 'X' beside a contact name 6. Verify a pop-up of 'WARNING Are you sure you want to remove this contact from this list?' 7. Click 'Cancel' and verify the group list is displayed with no changes 8. Select the 'X' beside a contact name 9. Verify a pop-up of 'WARNING Are you sure you want to remove this contact from this list?' 10. Click 'Continue' 11. Verify the contact was deleted from the group |  | RC |  |  |  |  | RC
Delete Contact Group | 1. Login to iQ as a State User 2. Select Admin > Contact Groups 3. In the Search box, start typing a contact group name 4. When the group appears, click to 'Expand' 5. Select the 'Delete' icon 6. Verify pop-up message of 'WARNING Are you sure you want to delete this contact list?' 7. Click 'Cancel' and verify the group list is displayed with no changes 8. Select the 'Delete' icon 9. Click 'Continue' 10. Verify the contact group was deleted |  | RC |  |  |  |  | RC

## Provider
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
Provider > Provider List
Provider List | 1. Login as a State User and select a provider 2. Click on Provider List 3. Verify the following tabs appear a. Pre-Discovery b. Onboarding c. Production |  | RC |  |  |  |  | RC
Pre-Discovery Tab
Pre-Discovery Tab DUE TO INTERFACE PROFILE FORM NOT WORKING, DO NOT COMPLETE STEPS 15-18 | 1. Verify the following appear: a. All Groups dropdown b. Add Provider button c. Search box d. Export icon e. Select a Stage to Set all Selected To dropdown f. Save All Selected button 2. Verify the All Groups drop down displays all organization groups 3. Select Add Provider and start typing a provider's name 4. Verify that only providers with those letters show in the list 5. Enter a PIN number and verify that the correct provider is in the list 6. Enter an address and verify that the correct provider is in the list 7. Select the checkbox for the Provider and click Cancel 8. Verify you are taken back to the Provider List 9. Select Add Provider and search for a provider by entering "Testing" 10. Select the checkbox by several providers and click Add 11. Expand the Pre-Discovery section 12. In the Search box, enter the first few characters for one of the added providers 13. Ensure the list is limited to the text entered 14. Delete the entry out of the Search box 15. Select the Export Icon 16. Verify pop-up message of 'Do you want to save provider_data_csv (xx.xx KB) from xxx.org? 17. Click Save As and save to desktop; then click Open 18. Verify that a CSV-formatted file of all the providers that have submitted their interface forms, along with each of the questions and answers on the form are visible. If no interface forms have been submitted, verify pop-up of 'There are no providers with submitted forms on this page' |  | RC |  |  |  |  | RC
Pre-Discovery Section | 1. Expand the Pre-Discovery Section 2. Verify the Onboarding Panel icon (feet) is visible at the beginning of the line 3. Verify the following columns are visible: a. Organization b. Facility c. City d. Rank e. Score f. Form g. Stage h. Checkbox column 4. Verify the following columns are sortable: a. Organization b. Facility c. City d. Rank e. Score f. Form 5. Change the rank on one organization and verify the list re-sorts 6. To verify the capability to change the stage on multiple organizations a. Scroll to the bottom of the section and click on "SELECT ALL" b. Verify the button changes to "DESELECT ALL" c. Click on "DESELECT ALL" and verify the check boxes are unchecked d. Verify the button changes to "SELECT ALL" and select it e. At the top of the section, select Wait-Listed Ready stage from the "Select a Stage to Set All Selected To" dropdown f. Select "SAVE ALL SELECTED" button 7. Verify that all the organizations selected were moved to the Wait-Listed Ready section |  | RC |  |  |  |  | RC
8. Confirm that at the bottom of the section, the option for next page is available and functional (if more than 10 organizations are in the section) 9. Click on the Onboarding Panel icon (feet) 10. Verify the Onboarding Panel appears 11. Click on menu area to close panel 12. Click on the provider's name (in blue) 13. Verify the Provider Profile page appears
Wait-Listed Ready | 1. Expand the Wait-Listed Ready Section 2. Verify the Onboarding Panel icon (feet) is visible at the beginning of the line 3. Verify the following columns are visible: a. Organization b. Facility c. City d. Rank e. Score f. Form g. Stage 4. Verify the following columns are sortable: a. Organization b. Facility c. City d. Rank e. Score f. Form 5. Change the rank on one organization and verify the list re-sorts 6. To verify the capability to change the stage on multiple organizations a. Scroll to the bottom of the section and click on "SELECT ALL" b. Verify the button changes to "DESELECT ALL" c. Click on "DESELECT ALL" and verify the check boxes are unchecked d. Verify the button changes to "SELECT ALL" and select it e. At the top of the section, select Wait-Listed Not Ready stage from the "Select a Stage to Set All Selected To" dropdown f. Select "SAVE ALL SELECTED" button 7. Verify that all the organizations selected were moved to the Wait-Listed Not Ready section |  | RC |  |  |  |  | RC
8. Confirm that at the bottom of the section, the option for next page is available and functional (if more than 10 organizations are in the section) 9. Click on the Onboarding Panel icon (feet) 10. Verify the Onboarding Panel appears 11. Click on menu area to close panel 12. Click on the provider's name (in blue) 13. Verify the Provider Profile page appears
Wait-Listed Not Ready | 1. Expand the Wait-Listed Not Ready Section 2. Verify the Onboarding Panel icon (feet) is visible at the beginning of the line 3. Verify the following columns are visible and sortable: a. Organization b. Facility c. City d. Rank e. Score f. Form g. Stage 4. Verify the following columns are sortable: a. Organization b. Facility c. City d. Rank e. Score f. Form 5. Change the rank on one organization and verify the list re-sorts 6. To verify the capability to change the stage on multiple organizations a. Scroll to the bottom of the section and click on "SELECT ALL" b. Verify the button changes to "DESELECT ALL" c. Click on "DESELECT ALL" and verify the check boxes are unchecked d. Verify the button changes to "SELECT ALL" and select it e. At the top of the section, select Wait-Listed Ready stage from the "Select a Stage to Set All Selected To" dropdown f. Select "SAVE ALL SELECTED" button 7. Verify that all the organizations selected were moved to the Wait-Listed Ready section |  | RC |  |  |  |  | RC
8. Confirm that at the bottom of the section, the option for next page is available and functional (if more than 10 organizations are in the section) 9. Click on the Onboarding Panel icon (feet) 10. Verify the Onboarding Panel appears 11. Click on menu area to close panel 12. Click on the provider's name (in blue) 13. Verify the Provider Profile page appears
Onboarding Tab
Onboarding Tab DUE TO INTERFACE PROFILE FORM NOT WORKING, DO NOT COMPLETE STEPS 8-10 | 1. Verify the following appear: a. All Groups dropdown b. Search box c. Export icon d. Select a Stage to Set all Selected To dropdown e. Save All Selected button 2. Verify the All Groups drop down displays all organization groups 3. Expand the Discovery section 4. In the Search box, enter the first few characters for one of the added providers 4. Ensure the list is limited to the text entered 6. Delete the entry out of the Search box 7. Select the Export Icon 8. Verify pop-up message of 'Do you want to save provider_data_csv (xx.xx KB) from xxx.org? 9. Click Save As and save to desktop; then click Open 10. Verify that a CSV-formatted file of all the providers that have submitted their interface forms, along with each of the questions and answers on the form are visible. If no interface forms have been submitted, verify pop-up of 'There are no providers with submitted forms on this page’ |  | RC |  |  |  |  | RC
Discovery | 1. Expand the Discovery Section 2. Verify the Onboarding Panel icon (feet) is visible at the beginning of the line 3. Verify the following columns are visible: a. Organization b. Facility c. City d. Rank e. Score f. Form g. Stage 4. Verify the following columns are sortable: a. Organization b. Facility c. City d. Rank e. Score f. Form 5. Change the rank on one organization and verify the list re-sorts 6. To verify the capability to change the stage on multiple organizations a. Scroll to the bottom of the section and click on "SELECT ALL" b. Verify the button changes to "DESELECT ALL" c. Click on "DESELECT ALL" and verify the check boxes are unchecked d. Verify the button changes to "SELECT ALL" and select it e. At the top of the section, select Planning stage from the "Select a Stage to Set All Selected To" dropdown f. Select "SAVE ALL SELECTED" button 7. Verify that all the organizations selected were moved to the Planning section |  | RC |  |  |  |  | RC
8. Confirm that at the bottom of the section, the option for next page is available and functional (if more than 10 organizations are in the section) 9. Click on the Onboarding Panel icon (feet) 10. Verify the Onboarding Panel appears 11. Click on menu area to close panel 12. Click on the provider's name (in blue) 13. Verify the Provider Profile page appears
Planning | 1. Expand the Planning Section 2. Verify the Onboarding Panel icon (feet) is visible at the beginning of the line 3. Verify the following columns are visible: a. Organization b. Facility c. City d. Rank e. Score f. Form g. Stage 4. Verify the following columns are sortable: a. Organization b. Facility c. City d. Rank e. Score f. Form 5. Change the rank on one organization and verify the list re-sorts 6. To verify the capability to change the stage on multiple organizations a. Scroll to the bottom of the section and click on "SELECT ALL" b. Verify the button changes to "DESELECT ALL" c. Click on "DESELECT ALL" and verify the check boxes are unchecked d. Verify the button changes to "SELECT ALL" and select it e. At the top of the section, select Development stage from the "Select a Stage to Set All Selected To" dropdown f. Select "SAVE ALL SELECTED" button 7. Verify that all the organizations selected were moved to the Development section |  | RC |  |  |  |  | RC
8. Confirm that at the bottom of the section, the option for next page is available and functional (if more than 10 organizations are in the section) 9. Click on the Onboarding Panel icon (feet) 10. Verify the Onboarding Panel appears 11. Click on menu area to close panel 12. Click on the provider's name (in blue) 13. Verify the Provider Profile page appears
Development | 1. Expand the Development Section 2. Verify the Onboarding Panel icon (feet) is visible at the beginning of the line 3. Verify the following columns are visible: a. Organization b. Facility c. City d. Rank e. Score f. Form g. Stage 4. Verify the following columns are sortable: a. Organization b. Facility c. City d. Rank e. Score f. Form 5. Change the rank on one organization and verify the list re-sorts 6. To verify the capability to change the stage on multiple organizations a. Scroll to the bottom of the section and click on "SELECT ALL" b. Verify the button changes to "DESELECT ALL" c. Click on "DESELECT ALL" and verify the check boxes are unchecked d. Verify the button changes to "SELECT ALL" and select it e. At the top of the section, select Testing stage from the "Select a Stage to Set All Selected To" dropdown f. Select "SAVE ALL SELECTED" button 7. Verify that all the organizations selected were moved to the Testing section |  | RC |  |  |  |  | RC
8. Confirm that at the bottom of the section, the option for next page is available and functional (if more than 10 organizations are in the section) 9. Click on the Onboarding Panel icon (feet) 10. Verify the Onboarding Panel appears 11. Click on menu area to close panel 12. Click on the provider's name (in blue) 13. Verify the Provider Profile page appears
Testing | 1. Expand the Testing Section 2. Verify the Onboarding Panel icon (feet) is visible at the beginning of the line 3. Verify the following columns are visible: a. Organization b. Facility c. City d. Rank e. Score f. Form g. Stage 4. Verify the following columns are sortable: a. Organization b. Facility c. City d. Rank e. Score f. Form 5. Change the rank on one organization and verify the list re-sorts 6. To verify the capability to change the stage on multiple organizations a. Scroll to the bottom of the section and click on "SELECT ALL" b. Verify the button changes to "DESELECT ALL" c. Click on "DESELECT ALL" and verify the check boxes are unchecked d. Verify the button changes to "SELECT ALL" and select it e. At the top of the section, select Pre-Go Live stage from the "Select a Stage to Set All Selected To" dropdown f. Select "SAVE ALL SELECTED" button 7. Verify that all the organizations selected were moved to the Pre-Go Live section |  | RC |  |  |  |  | RC
8. Confirm that at the bottom of the section, the option for next page is available and functional (if more than 10 organizations are in the section) 9. Click on the Onboarding Panel icon (feet) 10. Verify the Onboarding Panel appears 11. Click on menu area to close panel 12. Click on the provider's name (in blue) 13. Verify the Provider Profile page appears
Pre-Go Live | 1. Expand the Pre-Go Live Section 2. Verify the Onboarding Panel icon (feet) is visible at the beginning of the line 3. Verify the following columns are visible: a. Organization b. Facility c. City d. Rank e. Score f. Form g. Stage 4. Verify the following columns are sortable: a. Organization b. Facility c. City d. Rank e. Score f. Form 5. Change the rank on one organization and verify the list re-sorts 6. To verify the capability to change the stage on multiple organizations a. Scroll to the bottom of the section and click on "SELECT ALL" b. Verify the button changes to "DESELECT ALL" c. Click on "DESELECT ALL" and verify the check boxes are unchecked d. Verify the button changes to "SELECT ALL" and select it e. At the top of the section, select Production stage from the "Select a Stage to Set All Selected To" dropdown f. Select "SAVE ALL SELECTED" button 7. Verify that all the organizations selected were moved to the Production section |  | RC |  |  |  |  | RC
8. Confirm that at the bottom of the section, the option for next page is available and functional (if more than 10 organizations are in the section) 9. Click on the Onboarding Panel icon (feet) 10. Verify the Onboarding Panel appears 11. Click on menu area to close panel 12. Click on the provider's name (in blue) 13. Verify the Provider Profile page appears
Production Tab
Production Tab DUE TO INTERFACE PROFILE FORM NOT WORKING, DO NOT COMPLETE STEPS 8-10 | 1. Verify the following appear: a. All Groups dropdown b. Search box c. Export icon d. Select a Stage to Set all Selected To dropdown e. Save All Selected button 2. Verify the All Groups drop down displays all organization groups 3. Expand the Discovery section 4. In the Search box, enter the first few characters for one of the added providers 4. Ensure the list is limited to the text entered 6. Delete the entry out of the Search box 7. Select the Export Icon 8. Verify pop-up message of 'Do you want to save provider_data_csv (xx.xx KB) from xxx.org? 9. Click Save As and save to desktop; then click Open 10. Verify that a CSV-formatted file of all the providers that have submitted their interface forms, along with each of the questions and answers on the form are visible. If no interface forms have been submitted, verify pop-up of 'There are no providers with submitted forms on this page’ |  | RC |  |  |  |  | RC
Production | 1. Click on the Production tab 2. Verify the Onboarding Panel icon (feet) is visible at the beginning of the line 3. Verify the following columns are visible: a. Organization b. Facility c. City d. Form e. Stage f. Checkbox column 4. Verify the following columns are sortable: a. Organization b. Facility c. City d. Form 5. To verify the capability to change the stage on multiple organizations a. Scroll to the bottom of the section and click on "SELECT ALL" b. Verify the button changes to "DESELECT ALL" c. Click on "DESELECT ALL" and verify the check boxes are unchecked d. Verify the button changes to "SELECT ALL" and select it e. At the top of the section, select Pre-Go Live stage from the "Select a Stage to Set All Selected To" dropdown f. Select "SAVE ALL SELECTED" button 6. Verify that all the organizations selected were moved to the Pre-Go Live section |  | RC |  |  |  |  | RC
7. Confirm that at the bottom of the section, the option for next page is available and functional (if more than 10 organizations are in the section) 8. Click on the Onboarding Panel icon (feet) 9. Verify the Onboarding Panel appears 10. Click on menu area to close panel 11. Click on the provider's name (in blue) 12. Verify the Provider Profile page appears
Provider Profile | 1. Login as a OC User and select Provider 2. Verify the Profile is visible |  | OC |  |  |  |  | OC
| 1. Login as a FC User and select Provider 2. Verify the Profile is visible |  | FC |  |  |  |  | FC
Provider Profile | 1. Login as a RC user 2. Select Provider > Provider List 3. Open the Pre-Discovery Tab and take note of an organization/facility that shows Form > Unassigned 4. In the Search bar enter that organization and facility 5. Select Provider > Profile > Provider Profile 6. Ensure the information on the Profile tab is accurate (you can verify that by logging into IWeb and searching on the facility for the details) 7. Add an an email on the line under Action Items Alert Options and click on the "+" 8. Verify the email addresses are listed 9. Click on Assign Interface Form 10. Verify pop-up of "Send a template email to the Primary Contact as well?" 11. Move toggle to Yes 12. Click Assign and verify that a draft email pops up with ability to add an email address and the email contains information to enable the user to login and complete the interface form 13. Select the Documents tab then attach a document 14. Verify the document was attached and able to be selected |  | RC |  |  |  |  | RC
| 1. Login as a OC user 2. Select Provider > Profile 3. Ensure the information on the Provider Page is accurate |  | OC
| 1. Login as a FC user 2. Select Provider > Profile 3. Ensure the information on the Provider Page is accurate |  | FC
Provider Interface Form Assignment | 1. Login as a RC User 2. Select Provider > Provider List 3. Click on a provider that has Unassigned in Form column 4. Scroll to bottom of page and click on 'Assign Interface Form' 5. Verify pop-up with "Send a template email to the Primary Contact as well? 6. Move toggle to Yes 7. Click Cancel 8. Verify you are back on the profile tab 9. Click on 'Assign Interface Form' 10. Verify pop-up of "Send a template email to the Primary Contact as well? 11. Move toggle to Yes 12. Click Assign 13. Verify pop-up of "Interface Form Assigned to Provider" 14. Verify the Organization and/or Facility are in the search box 15. Verify the interface form was assigned by the Interface Form vX.0 tab being visible | Rae | RC |  |  |  | Mara | RC
Provider Interface Form Completion | 1. Login as a RC User 2. In the Search box, enter the organization that you assigned the interface form to above 3. Navigate to Provider > Provider Profile 4. Verify the Interface Form vX.0 is visible 5. Click on the Interface Form tab 6. On the Provider Info tab complete a couple questions but not a required question (shown with an "*") 7. Click Save 8. Verify pop up of "Changes successfully made" 9. Click Submit 10. Verify a pop up of "Not all required questions are answered" and there is a list of all the Required Unanswered Questions 11. Go back to interface form and fill out all the required questions 12. Verify a pop up of "WARNING The provider will no longer be able to make changes if you submit" 13. Click Continue and verify pop up of "Form Successfully Submitted" |  | RC |  |  |  |  | OC
| 1. Login as a OC User with Interface Form role for the Provider that was recently assigned the Interface Form 2. Ensure the user is not able to see State-Only questions 3. Select Answers to questions that have a score associated then click Save 4. Verify pop up of "Changes successfully made" 5. Logout and log back in as the same Provider User and ensure the answers selected were saved 6. Click Submit 7. Verify a pop up of "Not all required questions are answered" and there is a list of all the Required Unanswered Questions 8. Go back to interface form and fill out all the required questions (sum the scored questions as you fill out the form) 9. Verify a pop up of "WARNING The provider will no longer be able to make changes if you submit" 10. Click Continue and verify pop up of "Form Successfully Submitted" 11. Ensure the Interface Form is not modifiable after successful submission 12. Logout and log back in as a State User then select the Provider List under Provider on the left-hand menu 13. Ensure the Score for the Provider that recently submitted the Interface Form is accurate based on the answers the Provider submitted 14. Select the Provider to access the Provider Page then select the Interface Form 15. Select answers for the State-Only questions then Save 16. Verify pop up of "Changes successfully made" |  | OC |  |  |  |  | OC
| 1. Login as a FC User with Interface Form role for the Provider that was recently assigned the Interface Form 2. Ensure the user is not able to see State-Only questions 3. Select Answers to questions that have a score associated then click Save 4. Verify pop up of "Changes successfully made" 5. Logout and log back in as the same Provider User and ensure the answers selected were saved 6. Click Submit 7. Verify a pop up of "Not all required questions are answered" and there is a list of all the Required Unanswered Questions 8. Go back to interface form and fill out all the required questions (sum the scored questions as you fill out the form) 9. Verify a pop up of "WARNING The provider will no longer be able to make changes if you submit" 10. Click Continue and verify pop up of "Form Successfully Submitted" 11. Ensure the Interface Form is not modifiable after successful submission 12. Logout and log back in as a State User then select the Provider List under Provider on the left-hand menu 13. Ensure the Score for the Provider that recently submitted the Interface Form is accurate based on the answers the Provider submitted 14. Select the Provider to access the Provider Page then select the Interface Form 15. Select answers for the State-Only questions then Save 16. Verify pop up of "Changes successfully made" |  | FC |  |  |  |  | FC

## Onboarding Panel
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
Onboarding Panel
Main Tab
Main Tab (DO NOT COMPLETE STEP 5) | 1. Login as a RC user 2. In the Search bar enter an organization and facility 3. Click on the Onboarding Panel icon (two feet) in the Toolbar 4. Verify the following fields are displayed at the top: a. ORG b. FAC c. Onboarding: # Days d. Stage & # Days e. Project Lead f. VFC g. Provider Type h. EHR i. MU Stage j. Transport Method k. HL7 l. Bi-Direction 5. Verfiy the fields are correct based on information submitted on the interface form 6. Verify the Stages dropdown have the correct stages listed based on stages listed in Admin > Onboarding > Select Onboarding Stages 7. Change the stage and verify the provider was moved to that Stage in Provider > Provider List 8. Verify the Rank is editable 9. Change the Rank and verify the provider was moved in Provider > Provider List 10. Click on Profile under Quick Links |  | RC |  |  |  |  | RC
11. Verify the Profile tab is displayed 12. Click on the Onboarding Panel icon (two feet) in the Toolbar 13. Select Interface Form under Quick Links 14. Verify the Interface Form vX.0 is displayed 15. Click on the Onboarding Panel icon (two feet) in the Toolbar 16. Select Documents under Quick Links 17. Verify the Documents tab is displayed 18. Click on the Onboarding Panel icon (two feet) in the Toolbar 19. Select DQA under Quick Links 20. Verify the DQA menu item is displayed
Tasks (Prior to completing this item, contacts will need to be added.) | 1. Click on the Onboarding Panel icon (two feet) in the Toolbar 2. Under Tasks, click the Add icon (+) 3. Click the dropdown for Add Task and verify the list is in the same order as in Onboarding > Standard Tasks 4. Select a Task, Due Date, and Priority Level 5. Click Submit. Verify pop-up of 'Please enter all the necessary information" 6. Enter a description and click Submit 7. Verify the task has been created 8. Add a task under each of the priority levels - add one with due date of next day and add one with due date of same day 9. Verify a task is displayed under each priority level and color coded accordingly based on High (red), Medium (yellow), and Low (green) and each due date is color coded based on In Queue (blue), Less than 7 Days (yellow), and Past Due (red) 10. Verify each tasks displays the Task name, Description, Stage, Due Date, and userid of person who entered the task 11.Start typing a task in the search box and verify the task list is limited to only the tasks that match the search 12. Clear Search box and verify the task list has all tasks 13. On one of the tasks, select the Delete icon (trash can) 14. Verify the task has been deleted 15. Add a few more tasks under each priority level with due dates of same day, next day and more than 7 days |  | RC |  |  |  |  | RC
16. On one of the task select the Email icon and verify the Email contact list includes all contacts from the Contacts tab 17. Check the box beside two contacts 18. Click Cancel and verify the Task tab is displayed 19. On one of the tasks, select the Email icon (mail) 20. Verify the Email contact list includes all contacts from the Contacts tab 21. Check the box beside two contacts 22. Click Send Email and verify an email window pops up with email addresses in the To box along with description of task 23. Click Cancel to return to Tasks tab 24. Check box before task and verify the task is no longer displayed 25. Check the Completed box and verify the completed task is displayed 26. To filter the tasks, click on the drop down in the top right that says "All" 27. Select In Queue and verify the tasks with the next day due date and same day due date are not shown 28. Select All and verify all tasks are shown 29. Select Less than 7 Days and verify the tasks with the next day due date are shown 30. Select All and verify all tasks are shown 31. Select Past Due and verify the tasks with the same day due date are shown 32. Select All and verify all tasks are shown
Notes | 1. Click on the Notes tab 2. Select the Add icon 3. On the Description line add a note 4. Click Cancel 6. Verify you are taken back to the Notes tab 7. Select the Add icon 8. On the Description line add a note 9. Select Submit and verify pop-up of 'Note Created' 10. Select the Add Icon and verify the Description box is empty 11. And a few more notes 12. Verify each note displays Stage, Date and userif of person who entered note 13. Start typing a note in the search box and verify the note list is limited to only the tasks that match the search 14. Clear Search box and verify the note list has all notes 15. Select the Delete icon on one of the Notes and verify the note is no longer displayed |  | RC |  |  |  |  | RC
Logs Tab
Logs Tab | 1. Click on the Logs tab 2. Verify that all tasks and notes that were added previously, are displayed on this tab 3. Verify Time, Action, Stage and User columns are displayed and sortable 4. Start typing a task or note in the search box and verify the log list is limited to only the tasks or notes that match the search 5. Clear Search box and verify the log list has all tasks and notes |  | RC |  |  |  |  | RC
Contacts Tab
Contact List | 1. Click on the Contacts tab 2. Click the Add icon (+) 3. Click Cancel and verify the Contacts screen is displayed 4. Click the Add icon (+) 5. Add information from all fields but the position. Click Create 6. Verify a message appears under Position that states, 'This field must not be blank' 7. Enter Position and click Create 8. Verify pop-up of 'Contact Saved' 9. Verify the contact was added to list 10. Verify the contact was also added to the Global Contacts by selecting Admin > Global Contacts 11. Select the Onboarding Panel icon 12. Click the Add icon (+) 13. Click on the Global Contacts tab 14. Verify that the list does not include a contact that has already been assigned to the provider 15. Check the box beside one of the contacts 16. Click Cancel and verify the Contact List is visible 17. Click the Add icon (+) 18. Click on the Global Contacts tab 19. Check the box beside one of the contacts |  | RC |  |  |  |  | RC
20. Select Add and verify pop-up of 'Contact added to Provider' 21. Verify the contact was added to list 22. Start typing a contact's name in the search box and verify the contact list is limited to only the contacts that match the search 23. Clear Search box and verify the contact list has all contacts assigned 24. Verify First Name, Last Name, Position, Phone, and Email columns are displayed 25. Verify First and Last Name are sortable 26. Select the Delete icon (X) at the end of the line for one of the contacts 27. Verify that contact was deleted from the list 28. Verify pop-up of 'Providers Removed from Contacts' 29. Verify the contact was not deleted from the Global Contacts by selecting Admin > Global Contacts 30. Check the box beside two of the contacts 31. The Send Email button displays; select 32. Verify an email opens with the email addresses are displayed in the To box
Contact Groups | 1. Click on Contact Groups 2. To add a contact group, check box beside 'Show other contact groups' 3. Determine which group to add and click on the add icon '+' 4. Verify the group was added under 'Project Contact Groups' 5. Verify Name, Description and Actions are displayed 6. Verify Name is sortable 7. Start typing a contact group name in the search box and verify the contact group name list is limited to only the groups that match the search 8. Clear Search box and verify the contact group list has all groups displayed 9. Click mail icon and verify an email is displayed with contacts of group listed in To box 10. Click the Delete icon and verify pop-up of WARNING Are you sure you want to remove this group from this project? 11. Click Cancel; verify Contact Groups page is displayed 12. Click the Delete icon and verify pop-up of WARNING Are you sure you want to remove this group from this project? 13. Click Continue and verify group was deleted from list |  | RC |  |  |  |  | RC

## Action Items
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
Search Criteria & Results
All & Start Date/Time - End Date/Time | 1. Login as a RC user and enter Org/Fac in search box that messages were imported for 3. Select Action Items and verify the following criteria fields are displayed: a. Status Filters - Error/Warning/All b. Due/Fixed c. Date Filters - Start Date/Start Time/End Date/End Time d. Search 3. Enter a date/time range to not include all the messages that imported and click Search 4. Verify that all messages are displayed that imported in the date/time entered - Errors & Warnings 5. Verify the following columns are displayed: a. HL7 Field b. HL7 Code c. Issue d. Type e. Recommendation f. Date/Time 6. Verify that the HL7 Field column is sortable 7. Verify this information is displayed: a. The word "Patient' b. First and Last Name c. (MRN: XXXXXX) 8. Check box under 'MARK AS FIXED' and verify actions are no longer displayed for that MRN 9. Move the toggle to 'FIXED', click Search and verify the MRN you marked as fixed is displayed |  | RC |  |  |  |  | RC
| 1. Login as a OC user and enter Fac in search box that messages were imported for 2. Select Action Items and verify the following criteria fields are displayed: a. Status Filters - Error/Warning/All b. Due/Fixed c. Date Filters - Start Date/Start Time/End Date/End Time d. Search 3. Enter a date/time range to not include all the messages that imported and click Search 4. Verify that all messages are displayed that imported in the date/time entered 5. Verify the following columns are displayed: a. HL7 Field b. HL7 Code c. Issue d. Type e. Recommendation f. Date/Time 6. Verify that the HL7 Field column is sortable 7. Verify this information is displayed: a. The word "Patient' b. First and Last Name c. (MRN: XXXXXX) 8. Check box under 'MARK AS FIXED' and verify actions are no longer displayed for that MRN 9. Move the toggle to 'FIXED' and verify the MRN you marked as fixed is displayed |  | OC |  |  |  |  | OC
| 1. Login as a FC user 2. Select Action Items and verify the following criteria fields are displayed: a. Status Filters - Error/Warning/All b. Due/Fixed c. Date Filters - Start Date/Start Time/End Date/End Time d. Search 3. Enter a date/time range to not include all the messages that imported and click Search 4. Verify that all messages are displayed that imported in the date/time entered 5. Verify the following columns are displayed: a. HL7 Field b. HL7 Code c. Issue d. Type e. Recommendation f. Date/Time 6. Verify that the HL7 Field column is sortable 7. Verify this information is displayed: a. The word "Patient' b. First and Last Name c. (MRN: XXXXXX) 8. Check box under 'MARK AS FIXED' and verify actions are no longer displayed for that MRN 9. Move the toggle to 'FIXED' and verify the MRN you marked as fixed is displayed |  | FC |  |  |  |  | FC
Errors | 1. Login as a RC user and enter Org/Fac in search box that messages were imported for in step 1 2. For search criteria, select Error, Due and date messages imported from above and click Search 3. Verify that all messages are displayed that erred on that date are displayed 4. Check box under 'MARK AS FIXED' and verify actions are no longer displayed for that MRN 5. Move the toggle to 'FIXED' and verify the MRN you marked as fixed is displayed |  | RC |  |  |  |  | RC
| 1. Login as a OC user and enter Fac in search box that messages were imported for in step 1 2. For search criteria, select Error, Due and date messages imported from above 3. Verify that all messages are displayed that erred on that date are displayed 4. Check box under 'MARK AS FIXED' and verify actions are no longer displayed for that MRN 5. Move the toggle to 'FIXED' and verify the MRN you marked as fixed is displayed |  | OC |  |  |  |  | OC
| 1. Login as a FC user 2. For search criteria, select Error, Due and date messages imported from above 3. Verify that all messages are displayed that erred on that date are displayed 4. Check box under 'MARK AS FIXED' and verify actions are no longer displayed for that MRN 5. Move the toggle to 'FIXED' and verify the MRN you marked as fixed is displayed |  | FC |  |  |  |  | FC
Warnings | 1. Login as a RC user and enter Org/Fac in search box that messages were imported for in step 1 2. For search criteria, select Warning, Due and date messages imported from above 3. Verify that all messages are displayed that received a warning on that date 4. Check box under 'MARK AS FIXED' and verify actions are no longer displayed for that MRN 5. Move the toggle to 'FIXED' and verify the MRN you marked as fixed is displayed |  | RC |  |  |  |  | RC
| 1. Login as a OC user and enter Fac in search box that messages were imported for in step 1 2. For search criteria, select Warning, Due and date messages imported from above 3. Verify that all messages are displayed that received a warning on that date 4. Check box under 'MARK AS FIXED' and verify actions are no longer displayed for that MRN 5. Move the toggle to 'FIXED' and verify the MRN you marked as fixed is displayed |  | OC |  |  |  |  | OC
| 1. Login as a FC user 2. For search criteria, select Warning, Due and date messages imported from above 3. Verify that all messages are displayed that received a warning on that date 4. Check box under 'MARK AS FIXED' and verify actions are no longer displayed for that MRN 5. Move the toggle to 'FIXED' and verify the MRN you marked as fixed is displayed |  | FC |  |  |  |  | FC

## HL7 Transaction Log Viewer
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
HL7 Transaction Log View | 1. Login to iQ as a State User and select the HL7 Transaction Log Viewer 2. Verify the following search criteria is displayed: a. Patient Name b. MRN c. Lot # d. Start Date e. End Date f. Search button |  | RC |  |  |  |  | RC
| 1. Login to iQ as an Organization User and select the HL7 Transaction Log Viewer 2. Verify the following search criteria is displayed: a. Patient Name b. MRN c. Lot # d. Start Date e. End Date f. Search button |  | OC |  |  |  |  | OC
| 1. Login to iQ as an Facility User and select the HL7 Transaction Log Viewer 2. Verify the following search criteria is displayed: a. Patient Name b. MRN c. Lot # d. Start Date e. End Date f. Search button |  | FC |  |  |  |  | FC
Patient Name Search | 1. On the iQ Dashboard > Search box select one of the organizations & facilities from the messages imported 2. Enter a Patient's Name that doesn't belong to the organization selected above 3. Try to enter the Start or End Date as a future date 4. Verify a future date is not able to be selected 5. Enter the date range of when the messages weren't imported 6. Click Search and verify the record did not display 7. Enter a Patient's Name that does belong to the organization selected above 8. Click Search and verify the record is displayed with these colums a. ID b. MRN c. Patient d. Lot # e. Organization f. Facility g. The latest Status h. Date/Time i. Details 9. Verify each message has a unique global identifier (ID) 10. Click on "Details" for each of the submitted records 11. Verify the HL7 message is displayed 12. Verify all or some of the following Transaction Events are displayed along with Status and Date/Time a. Authentication b. HL7 Validation c. Issue Resolution Validation d. Processing in the IIS e. Saved in IIS |  | RC |  |  |  |  | RC
| 1. Log in as an Organization Client User 2. On the iQ Dashboard > Ensure the correct organization is displayed 3. Enter a Patient's Name that doesn't belong to the organization 4. Enter the date range of when the messages imported 5. Click Search 6. Verify the record did not display 7. Enter a Patient's Name that does belong to the organization 8. Click Search 9. Verify the record is displayed with these colums a. ID b. MRN c. Patient d. Lot # e. Organization f. Facility g. The latest Status h. Date/Time i. Details 10. Verify each message has a unique global identifier (ID) 11. Click on "Details" for each of the submitted records 12. Verify the HL7 message is displayed 13. Verify all or some of the following Transaction Events are displayed along with Status and Date/Time a. Authentication b. HL7 Validation c. Issue Resolution Validation d. Processing in the IIS e. Saved in IIS |  | OC |  |  |  |  | OC
| 1. Log in as a Facility Client User 2. On the iQ Dashboard > Ensure the correct organization and facility is displayed 3. Enter a Patient's Name that doesn't belong to the facility 4. Enter the date range of when the messages imported 5. Click Search 6. Verify the record did not display 7. Enter a Patient's Name that does belong to the facility 8. Click Search 9. Verify the record is displayed with these colums a. ID b. MRN c. Patient d. Lot # e. Organization f. Facility g. The latest Status h. Date/Time i. Details 10. Verify each message has a unique global identifier (ID) 11. Click on "Details" for each of the submitted records 12. Verify the HL7 message is displayed 13. Verify all or some of the following Transaction Events are displayed along with Status and Date/Time a. Authentication b. HL7 Validation c. Issue Resolution Validation d. Processing in the IIS e. Saved in IIS |  | FC |  |  |  |  | FC
MRN Search | 1. On the iQ Dashboard > Search box select another one of the organization & facility from the messages imported 2. Enter a MRN that doesn't belong to the organization selected above 3. Enter the date range of when the messages imported 4. Click Search 5. Verify the record did not display 6. Enter a MRN that does belong to the organization selected above 7. Click Search 8. Verify the record is displayed with these colums a. ID b. MRN c. Patient d. Lot # e. Organization f. Facility g. The latest Status h. Date/Time i. Details 9. Verify each message has a unique global identifier (ID) 10. Click on "Details" for each of the submitted records 11. Verify the HL7 message is displayed 12. Verify all or some of the following Transaction Events are displayed along with Status and Date/Time a. Authentication b. HL7 Validation c. Issue Resolution Validation d. Processing in the IIS e. Saved in IIS |  | RC |  |  |  |  | RC
| 1. Log in as an Organization Client User 2. On the iQ Dashboard > Ensure the correct organization is displayed 3. Enter a MRN that doesn't belong to the organization 4. Enter the date range of when the messages imported 5. Click Search 6. Verify the record did not display 7. Enter a MRN that does belong to the organization 8. Click Search 9. Verify the record is displayed with these colums a. ID b. MRN c. Patient d. Lot # e. Organization f. Facility g. The latest Status h. Date/Time i. Details 10. Verify each message has a unique global identifier (ID) 11. Click on "Details" for each of the submitted records 12. Verify the HL7 message is displayed 13. Verify all or some of the following Transaction Events are displayed along with Status and Date/Time a. Authentication b. HL7 Validation c. Issue Resolution Validation d. Processing in the IIS e. Saved in IIS |  | OC |  |  |  |  | OC
| 1. Log in as a Facility Client User 2. On the iQ Dashboard > Ensure the correct organization and facility is displayed 3. Enter a MRN that doesn't belong to the facility 4. Enter the date range of when the messages imported 5. Click Search 6. Verify the record did not display 7. Enter a MRN that does belong to the facility 8. Click Search 9. Verify the record is displayed with these colums a. ID b. MRN c. Patient d. Lot # e. Organization f. Facility g. The latest Status h. Date/Time i. Details 10. Verify each message has a unique global identifier (ID) 11. Click on "Details" for each of the submitted records 12. Verify the HL7 message is displayed 13. Verify all or some of the following Transaction Events are displayed along with Status and Date/Time a. Authentication b. HL7 Validation c. Issue Resolution Validation d. Processing in the IIS e. Saved in IIS |  | FC |  |  |  |  | FC
Lot Number Search | 1. On the iQ Dashboard > Search box select another one of the organization & facility from the messages imported 2. Enter a Lot # that doesn't belong to the organization selected above 3. Enter the date range of when the messages imported 4. Click Search 5. Verify the record did not display 6. Enter a Lot # that does belong to the organization selected above 7. Click Search 8. Verify the record is displayed with these colums a. ID b. MRN c. Patient d. Lot # e. Organization f. Facility g. The latest Status h. Date/Time i. Details 9. Verify each message has a unique global identifier (ID) 10. Click on "Details" for each of the submitted records 11. Verify the HL7 message is displayed 12. Verify all or some of the following Transaction Events are displayed along with Status and Date/Time a. Authentication b. HL7 Validation c. Issue Resolution Validation d. Processing in the IIS e. Saved in IIS |  | RC |  |  |  |  | RC
| 1. Log in as an Organization Client User 2. On the iQ Dashboard > Ensure the correct organization is displayed 3. Enter a Lot # that doesn't belong to the organization 4. Enter the date range of when the messages imported 5. Click Search 6. Verify the record did not display 7. Enter a Lot # that does belong to the organization 8. Click Search 9. Verify the record is displayed with these colums a. ID b. MRN c. Patient d. Lot # e. Organization f. Facility g. The latest Status h. Date/Time i. Details 10. Verify each message has a unique global identifier (ID) 11. Click on "Details" for each of the submitted records 12. Verify the HL7 message is displayed 13. Verify all or some of the following Transaction Events are displayed along with Status and Date/Time a. Authentication b. HL7 Validation c. Issue Resolution Validation d. Processing in the IIS e. Saved in IIS |  | OC |  |  |  |  | OC
| 1. Log in as a Facility Client User 2. On the iQ Dashboard > Ensure the correct organization and facility is displayed 3. Enter a Lot # that doesn't belong to the facility 4. Enter the date range of when the messages imported 5. Click Search 6. Verify the record did not display 7. Enter a Lot # that does belong to the facility 8. Click Search 9. Verify the record is displayed with these colums a. ID b. MRN c. Patient d. Lot # e. Organization f. Facility g. The latest Status h. Date/Time i. Details 10. Verify each message has a unique global identifier (ID) 11. Click on "Details" for each of the submitted records 12. Verify the HL7 message is displayed 13. Verify all or some of the following Transaction Events are displayed along with Status and Date/Time a. Authentication b. HL7 Validation c. Issue Resolution Validation d. Processing in the IIS e. Saved in IIS |  | FC |  |  |  |  | FC
Transaction Events are color coded correctly | 1. On the iQ Dashboard > Search box select one of the organization & facility from the messages imported that had a message that went to the ambiguous IDs and/or manual dedup queue 2. Enter adate range of when the messages imported 3. Click Search 4. Click on "Details" for the message 5. Verify the HL7 message is displayed 6. Verify the following Transaction Events are displayed with correct Status, Status color code, and Date/Time a. Authentication - Pass/dark green b. HL7 Validation - Pass/dark green c. Issue Resolution Validation - Pass/dark green d. Processing in the IIS - Processing/Light Green |  | RC |  |  |  |  | RC
| 1. Log in as an OC user 2. Enter a date range of when the messages imported that had a message that went to the ambiguous IDs and/or manual dedup queue 3. Click Search 4. Click on "Details" for the message 5. Verify the HL7 message is displayed 6. Verify the following Transaction Events are displayed with correct Status, Status color code, and Date/Time a. Authentication - Pass/dark green b. HL7 Validation - Pass/dark green c. Issue Resolution Validation - Pass/dark green d. Processing in the IIS - Processing/Light Green |  | OC |  |  |  |  | OC
| 1. Log in as an FC user 2. Enter a date range of when the messages imported that had a message that went to the ambiguous IDs and/or manual dedup queue 3. Click Search 4. Click on "Details" for the message 5. Verify the HL7 message is displayed 6. Verify the following Transaction Events are displayed with correct Status, Status color code, and Date/Time a. Authentication - Pass/dark green b. HL7 Validation - Pass/dark green c. Issue Resolution Validation - Pass/dark green d. Processing in the IIS - Processing/Light Green |  | FC |  |  |  |  | FC

## DQA
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
DQA TOOL
Search Page | 1. Verify the following are displayed: a. Print icon b. Export icon c. Filter icon d. Filter by: Year e. EHR Vendor, Import Profile ID, Connectivity User (only visible to RC users) f. Age Under 19 toggle g. HL7 Message location: Segment, Component, Field h. Search (not enabled) i. Reset j. Search icon with message of 'Please select a Year, a Time Frequency, and a HL7 Message Location 2. Verify when Year is selected, Time Frequency is displayed 3. Verify when Time Frequency of 'Quarterly' is selected, the Quarter dropdown displays 1, 2, 3, 4 4. Verify when Time Frequency of 'Monthly' is selected, the Month dropdown displays all the months 5. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 6. Select a 'Month' that encompasses the messages imported 8. Verify the Search button is not enabled 9. Move Age Under 19 toggle to the right 10. Select 'Field' for HL7 Message Location 11. Verify the Search button is now enabled 12. Click on the Filter icon and verify the filter criteria is not displayed 13. Click the Reset button and verify the previously entered criteria is cleared |  | RC |  |  |  |  | RC
| Login as Org User and follow steps above |  | OC |  |  |  |  | OC
| Login as Fac User and follow steps above |  | FC |  |  |  |  | FC
DQA by Field | 1. In the Search Bar, select Organization and Facility 2. DQA > Select the Year, Month, and 10-Day Interval that encompasses the messages that have been imported 3. Move Age Under 19 toggle to the right (to include only patients under 19) 4. Select Field for HL7 Message Location 5. Select 'Search' 6. Verify the information is calculated correctly and displayed in DQA Summary as: a. Total HL7 messages with PID segment received b. HL7 messages with successful transactions c. Hl7 message Success Rate d. HL7 messages with failed tranactions e. HL7 message Failure Rate 7. Verify that DQA Report is displayed as: a. PATIENT INFORMATION b. PATIENT NEXT OF KIN INFORMATION c. PATIENT VACCINATION INFORMATION d. PATIENT CONTRAINDICATION/EXAMPLE/HISTORY INFORMATION e. PATIENT GUARDIAN |  | RC |  |  |  |  | RC
8. For all sections above test for all steps listed below. 9. Verify each section is displayed as: a. HL7 Data Element b. HL7 Code c. Success (Rate) d. State Expectation e. Score f. Errors (Rate) g. Warnings (Rate) 10. For the data elements that appear in the DQA, Verify the State Expectations match the DQA setup in Admin 11. Verify there is a hyperlink for any HL7 Data Element with an error or warning 12. Verify that when you select a hyperlink, a pop-up window is displayed with a. A chart showing each error and warning with # of each b. HL7 Field (sortable) c. HL7 Code d. Issue e. Type f. Recommendation (Verify recommendation matches setup in Admin > DQA) g. Date/Time h. Patient Name & MRN i. MARK AS FIXED checkbox 13. Verify number of errors/warnings match the total number on chart and matches the number of HL7 Fields listed
14. Select the Print icon and print page one 15. Verify Time Period, Org, Fac, and search criteria is displayed at the top 16. Verify DQA Summary & DQA Report are displayed in a readable format 17. Verify when the Export icon is selected the following is displayed: pdf, xlsx, csv 18. Click on each and verify the approriate information is displayed and readable 19. Select the Year, Month, and 10-Day Interval that encompasses the messages that have been imported 20. Select Field for HL7 Message Location 21. Select 'Search' 22. Click on the same hyperlink as you did above and verify the chart has the correct number of errors/warnings and percentage. 23. Select the Year, Month, and 10-Day Interval that encompasses the messages that have been imported 24. Move Age Under 19 toggle to the right 25. Select Field for HL7 Message Location 26. Select 'Search' 27. Click on the same hyperlink as you did above and verify the chart has the correct number of errors/warnings and percentage. 28. To ensure changes made to the DQA recommendations and threshold are refleced in the DQA a. Take note of a warning or error identified in the previous DQA ran above b. Navigate to Admin > DQA c. Find the issue resolution from step a and update the state expectation and recommendations d. Run the DQA and ensure the changes you made were updated in the DQA
| Login as Org User and follow steps 2-28 |  | OC |  |  |  |  | OC
| Login as Fac User and follow steps 2-28 |  | FC |  |  |  |  | FC
DQA by Segment | 1. In Search bar, select Organization and Facility 2. Select the Year and Quarter that encompasses the messages that have been imported 3. Select Field for HL7 Message Location 4. Select 'Search' 5. Verify the information is calculated correctly and displayed in DQA Summary as: a. Total HL7 messages with PID segment received b. HL7 messages with successful transactions c. Hl7 message Success Rate d. HL7 messages with failed tranactions e. HL7 message Failure Rate 6. Verify that DQA Report is displayed as: a. PATIENT INFORMATION b. PATIENT VACCINATION INFORMATION 7. For all sections above test for all steps listed below. 8. Verify each section is displayed as: a. HL7 Data Element b. HL7 Code c. Success (Rate) d. State Expectation e. Score f. Errors (Rate) g. Warnings (Rate) |  | RC |  |  |  |  | RC | Pass
9. Verify the are entries under Patient Information and Patient Vaccination Information 10. Verify the State Expectations match the DQA setup in Admin 11. Verify there is a hyperlink for any segments missing 12. Verify that when you select a hyperlink, a pop-up window is displayed with a. A chart showing each error or warning with # of each b. HL7 Field c. HL7 Code d. Issue e. Type f. Recommendation (Verify recommendation matches setup in Admin > DQA) g. Date/Time h. Patient Name & MRN i. MARK AS FIXED checkbox 13. Verify number of errors/warnings match the total number on chart and matches the number of HL7 Segments listed 14. Select the Print icon and print page one 15. Verify Time Period, Org, Fac, and search criteria is displayed at the top 16. Verify DQA Summary & DQA Report are displayed in a readable format 17. Verify when the Export icon is selected the following is displayed: pdf, xlsx, csv 18. Click on each and verify the approriate information is displayed and readable
| Login as Org User and follow steps 2-18 |  | OC |  |  |  |  | OC
| Login as Fac User and follow steps 2-18 |  | FC |  |  |  |  | FC
DQA by Component | 1. In Search Bar, select Organization and Facility 2. Select the Year and 10 Day Interval that encompasses the messages that have been imported 3. Move Age Under 19 toggle to the right 4. Select Field for HL7 Message Location 5. Select 'Search' 6. Verify the information is calculated correctly and displayed in DQA Summary as: a. Total HL7 messages with PID segment received b. HL7 messages with successful transactions c. Hl7 message Success Rate d. HL7 messages with failed tranactions e. HL7 message Failure Rate 7. Verify that DQA Report is displayed as: a. PATIENT INFORMATION b. PATIENT NEXT OF KIN INFORMATION c. PATIENT VACCINATION INFORMATION d. PATIENT CONTRAINDICATION/EXAMPLE/HISTORY INFORMATION e. PATIENT GUARDIAN |  | RC |  |  |  |  | RC
8. For all sections above test for all steps listed below. 9. Verify each section is displayed as: a. HL7 Data Element b. HL7 Code c. Success (Rate) d. State Expectation e. Score f. Errors (Rate) g. Warnings (Rate) 10. Verify the HL7 Data Elements listed match the HL7 Data Elements listed in the Admin > DQA 11. Verify the State Expectations match the DQA setup in Admin 12. Verify there is a hyperlink for any HL7 Data Element with an error or warning 13. Verify that when you select a hyperlink, a pop-up window is displayed with a. A chart showing each error and warning with # of each b. HL7 Field (sortable) c. HL7 Code d. Issue e. Type f. Recommendation (Verify recommendation matches setup in Admin > DQA) g. Date/Time h. Patient Name & MRN i. MARK AS FIXED checkbox
14. Verify number of errors/warnings match the total number on chart and matches the number of HL7 Components listed 15. Select the Print icon and print page one 16. Verify Time Period, Org, Fac, and search criteria is displayed at the top 17. Verify DQA Summary & DQA Report are displayed in a readable format 18. Verify when the Export icon is selected the following is displayed: pdf, xlsx, csv 19. Click on each and verify the approriate information is displayed and readable 20. Select the Year and Month that encompasses the messages that have been imported 21. Select Field for HL7 Message Location 22. Select 'Search' 23. Click on the same hyperlink as you did above and verify the chart has the correct number of errors/warnings and percentage. 24. Select the Year and Quarter that encompasses the messages that have been imported 25. Move Age Under 19 toggle to the right 26. Select Field for HL7 Message Location 27. Select 'Search' 28. Click on the same hyperlink as you did above and verify the chart has the correct number of errors/warnings and percentage.
| Login as Org User and follow steps 2-28 above |  | OC |  |  |  |  | OC
| Login as Fac User and follow steps 2-28 above |  | FC |  |  |  |  | FC
DQA by EHRVendor | 1. Select the Year and 10 Day Interval that encompasses the messages that have been imported 2. Move Age Under 19 toggle to the right 3. Select a EHR Vendor that was used in the messages 4. Select Field for HL7 Message Location 5. Select 'Search' 6. Verify the information is calculated correctly and displayed in DQA Summary as: a. Total HL7 messages with PID segment received b. HL7 messages with successful transactions c. Hl7 message Success Rate d. HL7 messages with failed tranactions e. HL7 message Failure Rate 7. Verify that DQA Report is displayed as: a. PATIENT INFORMATION b. PATIENT NEXT OF KIN INFORMATION c. PATIENT VACCINATION INFORMATION d. PATIENT CONTRAINDICATION/EXAMPLE/HISTORY INFORMATION e. PATIENT GUARDIAN |  | RC |  |  |  |  | RC
8. For all sections above test for all steps listed below. 9. Verify each section is displayed as: a. HL7 Data Element b. HL7 Code c. Success (Rate) d. State Expectation e. Score f. Errors (Rate) g. Warnings (Rate) 10. Verify the HL7 Data Elements listed match the HL7 Data Elements listed in the Admin > DQA 11. Verify the State Expectations match the DQA setup in Admin 12. Verify there is a hyperlink for any HL7 Data Element with an error or warning 13. Verify that when you select a hyperlink, a pop-up window is displayed with a. A chart showing each error and warning with # of each b. HL7 Field (sortable) c. HL7 Code d. Issue e. Type f. Recommendation (Verify recommendation matches setup in Admin > DQA) g. Date/Time h. Patient Name & MRN i. MARK AS FIXED checkbox
14. Verify number of errors/warnings match the total number on chart and matches the number of HL7 Components listed 15. Select the Print icon and print page one 16. Verify Time Period, Org, Fac, and search criteria is displayed at the top 17. Verify DQA Summary & DQA Report are displayed in a readable format 18. Verify when the Export icon is selected the following is displayed: pdf, xlsx, csv 19. Click on each and verify the approriate information is displayed and readable 20. Select the Year and Month that encompasses the messages that have been imported 21. Select Field for HL7 Message Location 22. Select 'Search' 23. Click on the same hyperlink as you did above and verify the chart has the correct number of errors/warnings and percentage. 24. Select the Year and Quarter that encompasses the messages that have been imported 25. Move Age Under 19 toggle to the right 26. Select Field for HL7 Message Location 27. Select 'Search' 28. Click on the same hyperlink as you did above and verify the chart has the correct number of errors/warnings and percentage.
DQA by Import Profile ID | 1. Select the Year and 10 Day Interval that encompasses the messages that have been imported 2. Move Age Under 19 toggle to the right 3. Select a Import Profile ID that was used in the messages 4. Select Field for HL7 Message Location 5. Select 'Search' 6. Verify the information is calculated correctly and displayed in DQA Summary as: a. Total HL7 messages with PID segment received b. HL7 messages with successful transactions c. Hl7 message Success Rate d. HL7 messages with failed tranactions e. HL7 message Failure Rate 7. Verify that DQA Report is displayed as: a. PATIENT INFORMATION b. PATIENT NEXT OF KIN INFORMATION c. PATIENT VACCINATION INFORMATION d. PATIENT CONTRAINDICATION/EXAMPLE/HISTORY INFORMATION e. PATIENT GUARDIAN |  | RC |  |  |  |  | RC
8. For all sections above test for all steps listed below. 9. Verify each section is displayed as: a. HL7 Data Element b. HL7 Code c. Success (Rate) d. State Expectation e. Score f. Errors (Rate) g. Warnings (Rate) 10. Verify the HL7 Data Elements listed match the HL7 Data Elements listed in the Admin > DQA 11. Verify the State Expectations match the DQA setup in Admin 12. Verify there is a hyperlink for any HL7 Data Element with an error or warning 13. Verify that when you select a hyperlink, a pop-up window is displayed with a. A chart showing each error and warning with # of each b. HL7 Field (sortable) c. HL7 Code d. Issue e. Type f. Recommendation (Verify recommendation matches setup in Admin > DQA) g. Date/Time h. Patient Name & MRN i. MARK AS FIXED checkbox
14. Verify number of errors/warnings match the total number on chart and matches the number of HL7 Components listed 15. Select the Print icon and print page one 16. Verify Time Period, Org, Fac, and search criteria is displayed at the top 17. Verify DQA Summary & DQA Report are displayed in a readable format 18. Verify when the Export icon is selected the following is displayed: pdf, xlsx, csv 19. Click on each and verify the approriate information is displayed and readable 20. Select the Year and Month that encompasses the messages that have been imported 21. Select Field for HL7 Message Location 22. Select 'Search' 23. Click on the same hyperlink as you did above and verify the chart has the correct number of errors/warnings and percentage. 24. Select the Year and Quarter that encompasses the messages that have been imported 25. Move Age Under 19 toggle to the right 26. Select Field for HL7 Message Location 27. Select 'Search' 28. Click on the same hyperlink as you did above and verify the chart has the correct number of errors/warnings and percentage.
DQA by Connectivity User | 1. Select the Year and 10 Day Interval that encompasses the messages that have been imported 2. Move Age Under 19 toggle to the right 3. Select a Connectivity User that was used in the messages 4. Select Field for HL7 Message Location 5. Select 'Search' 6. Verify the information is calculated correctly and displayed in DQA Summary as: a. Total HL7 messages with PID segment received b. HL7 messages with successful transactions c. Hl7 message Success Rate d. HL7 messages with failed tranactions e. HL7 message Failure Rate 7. Verify that DQA Report is displayed as: a. PATIENT INFORMATION b. PATIENT NEXT OF KIN INFORMATION c. PATIENT VACCINATION INFORMATION d. PATIENT CONTRAINDICATION/EXAMPLE/HISTORY INFORMATION e. PATIENT GUARDIAN |  | RC |  |  |  |  | RC
8. For all sections above test for all steps listed below. 9. Verify each section is displayed as: a. HL7 Data Element b. HL7 Code c. Success (Rate) d. State Expectation e. Score f. Errors (Rate) g. Warnings (Rate) 10. Verify the HL7 Data Elements listed match the HL7 Data Elements listed in the Admin > DQA 11. Verify the State Expectations match the DQA setup in Admin 12. Verify there is a hyperlink for any HL7 Data Element with an error or warning 13. Verify that when you select a hyperlink, a pop-up window is displayed with a. A chart showing each error and warning with # of each b. HL7 Field (sortable) c. HL7 Code d. Issue e. Type f. Recommendation (Verify recommendation matches setup in Admin > DQA) g. Date/Time h. Patient Name & MRN i. MARK AS FIXED checkbox
14. Verify number of errors/warnings match the total number on chart and matches the number of HL7 Components listed 15. Select the Print icon and print page one 16. Verify Time Period, Org, Fac, and search criteria is displayed at the top 17. Verify DQA Summary & DQA Report are displayed in a readable format 18. Verify when the Export icon is selected the following is displayed: pdf, xlsx, csv 19. Click on each and verify the approriate information is displayed and readable 20. Select the Year and Month that encompasses the messages that have been imported 21. Select Field for HL7 Message Location 22. Select 'Search' 23. Click on the same hyperlink as you did above and verify the chart has the correct number of errors/warnings and percentage. 24. Select the Year and Quarter that encompasses the messages that have been imported 25. Move Age Under 19 toggle to the right 26. Select Field for HL7 Message Location 27. Select 'Search' 28. Click on the same hyperlink as you did above and verify the chart has the correct number of errors/warnings and percentage.
Actionable DQA | 1. Select Organization and Facility 2. Select the Year, Month, and 10-Day Interval that encompasses the messages that have been imported 3. Select Field for HL7 Message Location 4. Select 'Search' 5. Select a hyperlink under Errors or Warnings 6. For one of the patients listed, check the Mark as Fixed box 7. Verify that patient is no longer listed |  | RC |  |  |  |  | RC
| 1. Select the Year, Month, and 10-Day Interval that encompasses the messages that have been imported 2. Select Field for HL7 Message Location 3. Select 'Search' 4. Select a hyperlink under Errors or Warnings 5. For one of the patients listed, check the Mark as Fixed box 6. Verify that patient is no longer listed |  | OC |  |  |  |  | OC
| 1. Select the Year, Month, and 10-Day Interval that encompasses the messages that have been imported 2. Select Field for HL7 Message Location 3. Select 'Search' 4. Select a hyperlink under Errors or Warnings 5. For one of the patients listed, check the Mark as Fixed box 6. Verify that patient is no longer listed |  | FC |  |  |  |  | FC

## Data Summary
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
Search Page | 1. Verify the following are displayed: a. Filter icon b. Year, Monthly, and current Month c. EHR Vendor, Import Profile ID, Connectivity User (only visible to RC users) d. Search e. Reset 2. Verify when Time Frequency of 'Month' is selected, the Month dropdown displays all the months 3. Verify when Time Frequency of 'Quarterly' is selected, the Quarter dropdown displays 1, 2, 3, 4 4. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 5. Verify the folliwng charts are displayed: a. HL7 MESSAGE MILESTONE TRACKER b. PATIENT RECORDS ACCEPTED BY IIS c. PATIENT RECORDS IN PROCESSING d. VACCINATION RECORDS RECEIVED BY THE IIS e. VACCINATION RECORDS ACCEPTED BY THE IIS f. RECORD ERRORS RECEIVED BY PHC-HUB g. TOP 5 RECORD ERRORS h. TOP 5 RECORD WARNINGS 6. Click on the Filter icon and verify the filter criteria is not displayed 7. Click the Reset button and verify the previously entered criteria is cleared |  | RC |  |  |  |  | RC
| Login as Org User and follow steps above |  | OC |  |  |  |  | OC
| Login as Fac User and follow steps above |  | FC |  |  |  |  | FC
HL7 Message Milestone Tracker | 1. Login to PHC-Hub as a RC User and submit HL7 VXU message(s) that will fail at HL7 Validation (Milestone 1) 2. Submit HL7 VXU message(s) that fail at Issue Resolution (Milestone 2) 3. Submit HL7 VXU message(s) that successfully reach the Staging tables for the IIS then run Deduplication through iWeb to process the submitted messages and save them to the IIS (Milestone 4) 4. Submit HL7 VXU message(s) that successfully pass Issue Resolution validation and reach the Staging tables for the IIS (Milestone 3) 5. Login to iQ, select org/fac and select the Data Summary Dashboard on the left-hand menu 6. Ensure the correct number of messages are counted for the different Milestones for the HL7 Message Milestone Tracker |  | RC |  |  |  |  | RC
| 1. Login to iQ, select fac and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of messages are counted for the different Milestones for the HL7 Message Milestone Tracker |  | OC |  |  |  |  | OC
| 1. Login to iQ and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of messages are counted for the different Milestones for the HL7 Message Milestone Tracker |  | FC |  |  |  |  | FC
Patient Records Accepted by IIS | 1. Login to PHC-Hub as a RC User and submit HL7 VXU message(s) for a Patient that is under 19 years of age and that is saved to the IIS as a New Patient 2. Submit another HL7 VXU message(s) for a Patient that is under 19 years of age and that is saved to the IIS as an Update to a Patient 3. Submit HL7 VXU message(s) for a Patient that is over 18 years of age and that is saved to the IIS as a New Patient 4. Submit another HL7 VXU message(s) for a Patient that is over 18 years of age and that is saved to the IIS as an Update to a Patient 5. Login to iQ, select org/fac and select the Data Summary Dashboard on the left-hand menu 6. Ensure the correct number of patients (New/Update) are counted for the Patient Records Accepted by IIS report as well as the breakdown of how many patients are 18 and under and 19 and older |  | RC |  |  |  |  | RC
| 1. Login to iQ, select fac and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of patients (New/Update) are counted for the Patient Records Accepted by IIS report as well as the breakdown of how many patients are 18 and under and 19 and older |  | OC |  |  |  |  | OC
| 1. Login to iQ and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of patients (New/Update) are counted for the Patient Records Accepted by IIS report as well as the breakdown of how many patients are 18 and under and 19 and older |  | FC |  |  |  |  | FC
Patient Records in Processing | 1. Login to PHC-Hub as a RC User and submit HL7 VXU message(s) that will be stuck in Ambiguous ID 2. Submit another HL7 VXU message(s) that will be stuck in Manual Deduplication 3. Login to iQ, select org/fac, and select the Data Summary Dashboard on the left-hand menu 4. Ensure the correct number of records are counted for the Patient Records in Processing report for messages in Ambiguous ID and in Manual Deduplication |  | RC |  |  |  |  | RC
| 1. Login to iQ, select fac, and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of records are counted for the Patient Records in Processing report for messages in Ambiguous ID and in Manual Deduplication |  | OC |  |  |  |  | OC
| 1. Login to iQ and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of records are counted for the Patient Records in Processing report for messages in Ambiguous ID and in Manual Deduplication |  | FC |  |  |  |  | FC
Vaccinations Records Received by the IIS | 1. Login to PHC-Hub as a RC User and submit HL7 VXU message(s) with a Vaccination(s) that is saved to the IIS as a New Vaccination 2. Submit another HL7 VXU message(s) with a Vaccination(s) that is saved to the IIS as a Update to a Vaccination 3. Login to iQ, select org/fac, and select the Data Summary Dashboard on the left-hand menu 4. Ensure the correct number of Vaccinations (New/Update) are counted for the Vaccination Records Received by the IIS report |  | RC |  |  |  |  | RC
| 1. Login to iQ, select fac, and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Vaccinations (New/Update) are counted for the Vaccination Records Received by the IIS report |  | OC |  |  |  |  | OC
| 1. Login to iQ and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Vaccinations (New/Update) are counted for the Vaccination Records Received by the IIS report |  | FC |  |  |  |  | FC
Vaccinations Records Accepted by the IIS | 1. Login to PHC-Hub as a RC User and submit HL7 VXU message(s) with a Historical Vaccination(s) that is saved to the IIS 2. Submit another HL7 VXU message(s) with an Administered Vaccination(s) that is saved to the IIS 3. Login to iQ, select org/fac, and select the Data Summary Dashboard on the left-hand menu 4. Ensure the correct number of Vaccinations (Historical/Administered) are counted for the Vaccination Records Accepted by the IIS report |  | RC |  |  |  |  | RC
| 1. Login to iQ, select fac, and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Vaccinations (Historical/Administered) are counted for the Vaccination Records Accepted by the IIS report |  | OC |  |  |  |  | OC
| 1. Login to iQ and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Vaccinations (Historical/Administered) are counted for the Vaccination Records Accepted by the IIS report |  | FC |  |  |  |  | FC
Record Errors Received by PHC-Hub | 1. Login to PHC-Hub as a RC User and submit HL7 VXU message(s) with Patient and Vaccination level errors and warnings that is saved to the IIS 2. Login to iQ, select org/fac, and select the Data Summary Dashboard on the left-hand menu 3. Ensure the correct number of Patient and Vaccinations Errors are counted for the Record Errors Received by PHC-Hub report |  | RC |  |  |  |  | RC
| 1. Login to iQ, select fac, and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Patient and Vaccinations Errors are counted for the Record Errors Received by PHC-Hub report |  | OC |  |  |  |  | OC
| 1. Login to iQ and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Patient and Vaccinations Errors are counted for the Record Errors Received by PHC-Hub report |  | FC |  |  |  |  | FC
Top 5 Record Errors | 1. Login to iQ, select org/fac, and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Errors are counted for the Top 5 Record Errors |  | RC |  |  |  |  | RC
| 1. Login to iQ, select fac, and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Errors are counted for the Top 5 Record Errors |  | OC |  |  |  |  | OC
| 1. Login to iQ and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Errors are counted for the Top 5 Record Errors |  | FC |  |  |  |  | FC
Top 5 Record Warnings | 1. Login to iQ, select org/fac, and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Warnings are counted for the Top 5 Record Warnings reports |  | RC |  |  |  |  | RC
| 1. Login to iQ, select fac, and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Warnings are counted for the Top 5 Record Warnings reports |  | OC |  |  |  |  | OC
| 1. Login to iQ and select the Data Summary Dashboard on the left-hand menu 2. Ensure the correct number of Warnings are counted for the Top 5 Record Warnings reports |  | FC |  |  |  |  | FC

## Trends (State)
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
Data Quality
Monthly Success Rate | 1. Log in to iQ as a State User and select Trends > Data Quality on the left-hand menu 2. Verify the Filter icon and Filter by Year is displayed 3. Ensure the Success Rate is equal to (Number of HL7 VXU Messages that are Saved in IIS/Total Number of HL7 VXU Messages Submitted) for the Monthly Success Rate 4. Click on bar in graph to verify the Daily Success Rate is displayed correctly. 5. Change the Filter By to a different year 6. Click Search and verify a message of 'No Data Available for Selected Criteria' 7. Select the Filter icon and verify the filter by fields are not displayed 8. Select the Reset button and verify the previously selected criteria is cleared |  | RC |  |  |  |  | RC
Organizations with the Lowest/Highest Percentage of Messages with Error | 1. Login to iQ as a RC user and select Trends > Data Quality on the left-hand menu 2. Verify the following is displayed: a. Filter icon b. Filter by: Year, Month, Current Month c. Search d. Reset 3. Verify when Time Frequency of 'Month' is selected, the Month dropdown displays all the months 4. Verify when Time Frequency of 'Quarterly' is selected, the Quarter dropdown displays 1, 2, 3, 4 5. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 6. Select the Month that will incorporate the messages that were imported 7. Ensure the correct Error Percentage is calculated for the different Organizations for the Organizations with the Lowest/Highest Percentage of Messages with Error reports by calculating (Number of HL7 VXU Messages submitted for the Organization that Fail at Issue Resolution/Total Number of HL7 VXU Messages submitted for the Organization that at least reach Processing in IIS) 8. Select the Table View and verify the following columns are displayed: Rank, Organization Name, Error %, Error Count, Warning %, Warning Count, HL7 Message Count and Performance 9. Ensure the correct counts and percentages for the Organizations are accurate 10. Select the frequency of 10-day Interval, month and the 10 day interval values that will incorporate the messages that were imported |  | RC |  |  |  |  | RC
11. Ensure the correct Error Percentage is calculated for the different Organizations for the Organizations with the Lowest/Highest Percentage of Messages with Error reports by calculating (Number of HL7 VXU Messages submitted for the Organization that Fail at Issue Resolution/Total Number of HL7 VXU Messages submitted for the Organization that at least reach Processing in IIS) 12. Select the frequency of quarter and a quarter value that will not incorporate the messages that were imported 13. Ensure a message of "No Data Available For Selected Criteria" is displayed 14. Select the Filter icon and verify the filter by fields are not displayed 15. Select the Reset button and verify the previously selected criteria is cleared
EHR Vendors with Lowest/Highest Percentage of Messages with Error | 1. Login to iQ as a State User and select the Data Quality Dashboard on the left-hand menu 2. Verify the following is displayed: a. Filter icon b. Filter by: Year, Month, Current Month c. Search d. Reset 3. Verify when Time Frequency of 'Month' is selected, the Month dropdown displays all the months 4. Verify when Time Frequency of 'Quarterly' is selected, the Quarter dropdown displays 1, 2, 3, 4 5. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 6. Select the Month that will incorporate the messages that were imported 7. Ensure the correct Error Percentage is calculated for the different Organizations for the Organizations with the Lowest/Highest Percentage of Messages with Error reports by calculating (Number of HL7 VXU Messages submitted for the Organization that Fail at Issue Resolution/Total Number of HL7 VXU Messages submitted for the Organization that at least reach Processing in IIS) 8. Select the Table View and verify the following columns are displayed: Rank, Organization Name, Error %, Error Count, Warning %, Warning Count and Total Messages 9. Ensure the correct counts and percentages for the Organizations are accurate 10. Select the frequency of 10-day Interval, month and the 10 day interval values that will incorporate the messages that were imported |  | RC |  |  |  |  | RC
11. Ensure the correct Error Percentage is calculated for the different Organizations for the Organizations with the Lowest/Highest Percentage of Messages with Error reports by calculating (Number of HL7 VXU Messages submitted for the Organization that Fail at Issue Resolution/Total Number of HL7 VXU Messages submitted for the Organization that at least reach Processing in IIS) 12. Select the frequency of quarter and a quarter value that will not incorporate the messages that were imported 13. Ensure a message of "No Data Available For Selected Criteria" is displayed 14. Select the Filter icon and verify the filter by fields are not displayed 15. Select the Reset button and verify the previously selected criteria is cleared
Data Element Quality
Top/Bottom 10 HL7 Data Elements | 1. Select Trends > Data Element Quality on the left-hand menu 2. Verify the following are displayed: a. Filter icon b. Filter by: Year, Month, Current Month c. HL7 Message location: Segment, Component, Field d. Search e. Reset 3. Verify when Time Frequency of 'Month' is selected, the Month dropdown displays all the months 4. Verify when Time Frequency of 'Quarterly' is selected, the Quarter dropdown displays 1, 2, 3, 4 5. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 6. Select the Month that will incorporate the messages that were imported 7. Ensure the Top/Bottom 10 HL7 Data Elements displays the Data Elements with the lowest/highest Error Rate sorted accordingly 8. Select the Table View and verify the following columns are displayed: Data Elements, Error %, # with Errors, Warning %, # with Warnings, Total # and Performance 9. Ensure the Top/Bottom 10 HL7 Data Elements metrics are accurate based on the submitted message(s) 10. Select the frequency of 10-day Interval, month and the 10 day interval values that will incorporate the messages that were imported 11. Select HL7 Message Location of 'Segment' and click Search |  | RC |  |  |  |  | RC
12. Ensure the Top/Bottom 3 segment metrics are accurate based on the submitted message(s) 13. Select the frequency Quarterly and select the Quarter that will incorporate the messages that were imported 14. Select HL7 Message Location of 'Component' and click Search 15. Ensure the Top/Bottom 10 HL7 Data Elements metrics are accurate based on the submitted message(s) 16. Select the Filter icon and verify the filter by fields are not displayed 17. Select the Reset button and verify the previously selected criteria is cleared
EHR Data Element Quality Comparison | 1. Select Trends > Data Element on the left-hand menu 2. Verify the following are displayed for EHR Comparison: a. Filter icon b. Filter by: Year, Month, Current Month c. Drop down boxes for Primary Vendor and 5 more vendors d. HL7 Message location: Segment, Component, Field e. Search f. Reset 3. Verify when Time Frequency 'Month' is selected, the dropdown displays the months 4. Verify when Time Frequency 'Quarterly' is selected, the dropdown displays 1, 2, 3, 4 5. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 6. Select the Month that will incorporate the messages that were imported 7. Select a Primary Vendor and at least one EHR 8. Select HL7 Message Location of 'Field' and click Search 9. Ensure the Error Rates are accurate 10. Select the frequency of 10-day Interval, month and the 10 day interval values that will incorporate the messages that were imported 11. Select HL7 Message Location of 'Segment' and click Search 12. Ensure the Error Rates are accurate 13. Select the frequency Quarterly and select the Quarter that will incorporate the messages that were imported 14. Select HL7 Message Location of 'Component' and click Search 15. Ensure the Error Rates are accurate 16. Select the Filter icon and verify the filter by fields are not displayed 17. Select the Reset button and verify the previously selected criteria is cleared |  | RC |  |  |  |  | RC
HL7 Data Element Comparison | 1. Login to iQ as a RC User 2. Select Trends > Data Element Quality on the left-hand menu 3. Verify the following are displayed for HL7 Data Element Comparison: a. Filter icon b. Filter by: Year c. Drop down box for HL7 Data Element selection d. HL7 Message location: Segment, Component, Field e. Search f. Reset 4. Select 6 data elements (hold CTRL key and select) 5. Verify only 5 data elements can be selected 6. Verify after selecting more than one element, the drop down has 'Multiple Selected' 7. Select Field and click Search 8. Ensure the Error Rates are accurate for the selected data elements 9. Click Reset 10. Select HL7 Message Location 'Component' 11. Select 1-5 data elements from the HL7 Data Element dropdown 12. Ensure the Error Rates are accurate for the selected data elements 13. Click Reset 14. Select HL7 Message Location 'Segments' 15. Select two or more segments from the HL7 Data Element dropdown 16. Ensure the Error Rates are accurate for the selected data elements 17. Select the Reset button and verify the appropriate criteria is available in the HL7 Data Element dropdown 18. Select the Filter icon and verify the filter by fields are not displayed |  | RC |  |  |  |  | RC
Data Volume
Data Volume
Monthly Message Tracker | 1. Login to iQ as a RC User and select Trends > Data Volume on the left-hand menu 2. Verify the following are displayed for Monthly Success Tracker: a. Filter icon b. Filter by: Year c. Drop down boxes for Message Type and Sub-Message Type d. Search e. Reset 3. Verify when 'Queries' is selected the Sub-Message Type displays only QBP & VXQ 4. Verify when 'Updates' is selected the Sub-Message Type displays only ADT, ORU, VXU 5. Ensure the correct number of messages are counted for the Monthly Message Tracker 6. Change the filters of the Message Type to Updates and ensure only ADT, ORU, and VXU messages are counted 7. Change the filters of the Message Type to Queries and ensure only QBP and VXQ messages are counted 8. Select the Filter icon and verify the filter by fields are not displayed 9. Select the Reset button and verify the previously selected criteria is cleared |  | RC |  |  |  |  | RC
Organizations with the Lowest/Highest Number of HL7 Message Submissions | 1. Login to iQ as a State User and select Trends > Data Volume on the left-hand menu 2. Verify the following are displayed for HL7 Message Submissioms: a. Filter icon b. Filter by: Year, Month, or 10-day interval c. Drop down boxes for Message Type and Sub-Message Type d. Search e. Reset 3. Verify when Time Frequency of 'Month' is selected, the Month dropdown displays all the months 4. Verify when Time Frequency of 'Quarterly' is selected, the Quarter dropdown displays 1, 2, 3, 4 5. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 6. Select the Month that will incorporate the messages that were imported 7. Ensure the correct number of messages are counted for the different Organizations for the Organization with Lowest/Highest Number of HL7 Message Submissions report 8. Select the Table View and verify the following columns are displayed: Rank, Organization Name, HL7 Message Count and Performance 9. Ensure the correct counts for the Organizations and the Facilities under the Organizations are counted 10. Change the filters of the Message Type to Updates and ensure only ADT, ORU, and VXU messages are counted 11. Change the filters of the Message Type to Queries and ensure only QBP and VXQ messages are counted 12. Select the Filter icon and verify the filter by fields are not displayed 13. Select the Reset button and verify the previously selected criteria is cleared |  | RC |  |  |  |  | RC
Milestone | 1. Login to iQ as a State User and select the Data Volume Dashboard under Trends on the left-hand menu 2. Verify the following are displayed for HL7 Message Submissioms: a. Filter icon b. Filter by: Year, Month, Current Month c. Search d. Reset 3. Verify when Time Frequency of 'Month' is selected, the Month dropdown displays all the months 4. Verify when Time Frequency of 'Quarterly' is selected, the Quarter dropdown displays 1, 2, 3, 4 5. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 6. Select the Month that will incorporate the messages that were imported 7. Ensure the correct number of messages are counted for the different Milestones for the Milestone Tracker 8. Select the Filter icon and verify the filter by fields are not displayed 9. Select the Reset button and verify the previously selected criteria is cleared |  | RC |  |  |  |  | RC
Organization Status
| 1.Login to iQ as a State User and select the Organization Status Dashboard under Trends on the left-hand menu 2. Verify the following are displayed: a. Healthcare Provider Count by Onboarding Stage b. Healthcare Provider Count by Meaningful Use Stages c. Healthcare Provider Count by HL7 Version 3. Ensure the correct numbers are counted for the each chart listed above 4. Select the Table View for each chart listed above and ensure the correct counts are displayed and verify the following columns are visible: Org Name, Facility Name, Onboarding Stage, HL7 Version, MU Stage, Contact Name, Transport Mechanism, Bi Directional (Yes/No), and VFC (Yes/No) |  | RC |  |  |  |  | RC

## Trends (OCFC)
Item/Scenario | Steps/Acceptance Criteria | Primary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments | Secondary Tester | Type of Account | Pass Fail | If Fail, HD Ticket # | Comments
Data Quality Progress
Monthly Success Rate | 1. Login to iQ as a OC User and select a facility 2. Select Trends > Data Quality on the left-hand menu 3. Verify the Filter icon and Filter by Year is displayed 4. Ensure the Success Rate is equal to (Number of HL7 VXU Messages that are Saved in IIS/Total Number of HL7 VXU Messages Submitted) for the Monthly Success Rate 5. Change the Filter By to a different year 6. Click Search and verify a message of 'No Data Available for Selected Criteria' 7. Select the Filter icon and verify the filter by fields are not displayed 8. Select the Reset button and verify the previously selected criteria is cleared |  | OC |  |  |  |  | OC
| 1. Login to iQ as a FC User 2. Select Trends > Data Quality on the left-hand menu 2. Verify the Filter icon and Filter by Year is displayed 3. Ensure the Success Rate is equal to (Number of HL7 VXU Messages that are Saved in IIS/Total Number of HL7 VXU Messages Submitted) for the Monthly Success Rate 4. Change the Filter By to a different year 5. Click Search and verify a message of 'No Data Available for Selected Criteria' 6. Select the Filter icon and verify the filter by fields are not displayed 7. Select the Reset button and verify the previously selected criteria is cleared |  | FC |  |  |  |  | FC
Data Element Quality
Top/Bottom 10 HL7 Data Elements | 1. Login to iQ as a OC User and select FAC 2. Select Trends > Data Element Quality on the left-hand menu 3. Verify the following are displayed: a. Filter icon b. Filter by: Year, Month, Current Month c. HL7 Message location: Segment, Component, Field d. Search e. Reset 5. Verify when Time Frequency 'Month' is selected, the Month dropdown displays all the months 6. Verify when Time Frequency 'Quarterly' is selected, the Quarter displays 1, 2, 3, 4 7. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 8. Select the Month that will incorporate the messages that were imported 10. Ensure the Top/Bottom 10 HL7 Data Elements displays the Data Elements with the lowest/highest Error Rate sorted accordingly 11. Select the Table View and verify the following columns are displayed: Data Elements, Error %, # with Errors, Warning %, # with Warnings, Total # and Performance 12. Ensure the Top/Bottom 10 HL7 Data Elements metrics are accurate based on the submitted message(s) 13. Select the frequency of 10-day Interval, month and the 10 day interval values that will incorporate the messages that were imported 14. Ensure the Top/Bottom 10 HL7 Data Elements metrics are accurate based on the submitted message(s) 15. Select the Filter icon and verify the filter by fields are not displayed 16. Select the Reset button and verify the previously selected criteria is cleared |  | OC |  |  |  |  | OC
| 1. Login to iQ as a FC User 2. Select Trends > Data Element Quality on the left-hand menu 3. Verify the following are displayed: a. Filter icon b. Filter by: Year, Month, Current Month c. HL7 Message location: Segment, Component, Field d. Search e. Reset 5. Verify when Time Frequency of 'Month' is selected, the Month dropdown displays all the months 6. Verify when Time Frequency 'Quarterly' is selected, the dropdown displays 1, 2, 3, 4 7. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 8. Select the Month that will incorporate the messages that were imported 10. Ensure the Top/Bottom 10 HL7 Data Elements displays the Data Elements with the lowest/highest Error Rate sorted accordingly 11. Select the Table View and verify the following columns are displayed: Data Elements, Error %, # with Errors, Warning %, # with Warnings, Total # and Performance 12. Ensure the Top/Bottom 10 HL7 Data Elements metrics are accurate based on the submitted message(s) 13. Select the frequency of 10-day Interval, month and the 10 day interval values that will incorporate the messages that were imported 14. Ensure the Top/Bottom 10 HL7 Data Elements metrics are accurate based on the submitted message(s) 15. Select the Filter icon and verify the filter by fields are not displayed 16. Select the Reset button and verify the previously selected criteria is cleared |  | FC |  |  |  |  | FC
HL7 Data Element Comparison | 1. Login to iQ as a OC User and select a facility 2. Select Trends > Data Element Quality on the left-hand menu 3. Verify the following are displayed for HL7 Data Element Comparison: a. Filter icon b. Filter by: Year c. Drop down box for HL7 Data Element selection d. HL7 Message location: Segment, Component, Field e. Search f. Reset 4. Select 6 data elements (hold CTRL key and select) 5. Verify only 5 data elements can be selected 6. Verify after selecting more than one element, the drop down has 'Multiple Selected' 7. Select Field and click Search 8. Ensure the Error Rates are accurate for the selected data elements 9. Click Reset 10. Select HL7 Message Location 'Component' 11. Select 1-5 data elements from the HL7 Data Element dropdown 12. Ensure the Error Rates are accurate for the selected data elements 13. Click Reset 14. Select HL7 Message Location 'Segments' 15. Select two or more segments from the HL7 Data Element dropdown 16. Ensure the Error Rates are accurate for the selected data elements 17. Select the Reset button and verify the appropriate criteria is available in the HL7 Data Element dropdown 18. Select the Filter icon and verify the filter by fields are not displayed |  | OC |  |  |  |  | OC
| 1. Login to iQ as a FC User 2. Select Trends > Data Element Quality on the left-hand menu 3. Verify the following are displayed for HL7 Data Element Comparison: a. Filter icon b. Filter by: Year c. Drop down box for HL7 Data Element selection d. HL7 Message location: Segment, Component, Field e. Search f. Reset 4. Select 6 data elements (hold CTRL key and select) 5. Verify only 5 data elements can be selected 6. Verify after selecting more than one element, the drop down has 'Multiple Selected' 7. Select Field and click Search 8. Ensure the Error Rates are accurate for the selected data elements 9. Click Reset 10. Select HL7 Message Location 'Component' 11. Select 1-5 data elements from the HL7 Data Element dropdown 12. Ensure the Error Rates are accurate for the selected data elements 13. Click Reset 14. Select HL7 Message Location 'Segments' 15. Select two or more segments from the HL7 Data Element dropdown 16. Ensure the Error Rates are accurate for the selected data elements 17. Select the Reset button and verify the appropriate criteria is available in the HL7 Data Element dropdown 18. Select the Filter icon and verify the filter by fields are not displayed |  | FC |  |  |  |  | FC
Data Volume
Monthly Success Tracker | 1. Login to iQ as a OC User and select a facility 2. Select Trends > Data Volume on the left-hand menu 3. Verify the following are displayed for Monthly Success Tracker: a. Filter icon b. Filter by: Year c. Drop down boxes for Message Type and Sub-Message Type d. Search e. Reset 4. Verify when 'Queries' is selected the Sub-Message Type displays only QBP & VXQ 5. Verify when 'Updates' is selected the Sub-Message Type displays only ADT, ORU, VXU 6. Ensure the correct number of messages are counted for the Monthly Message Tracker 7. Change the filters of the Message Type to Updates and ensure only ADT, ORU, and VXU messages are counted 8. Change the filters of the Message Type to Queries and ensure only QBP and VXQ messages are counted 9. Select the Filter icon and verify the filter by fields are not displayed 10. Select the Reset button and verify the previously selected criteria is cleared |  | OC |  |  |  |  | OC
| 1. Login to iQ as a FC User 2. Select Trends > Data Volume on the left-hand menu 3. Verify the following are displayed for Monthly Success Tracker: a. Filter icon b. Filter by: Year c. Drop down boxes for Message Type and Sub-Message Type d. Search e. Reset 4. Verify when 'Queries' is selected the Sub-Message Type displays only QBP & VXQ 5. Verify when 'Updates' is selected the Sub-Message Type displays only ADT, ORU, VXU 6. Ensure the correct number of messages are counted for the Monthly Message Tracker 7. Change the filters of the Message Type to Updates and ensure only ADT, ORU, and VXU messages are counted 8. Change the filters of the Message Type to Queries and ensure only QBP and VXQ messages are counted 9. Select the Filter icon and verify the filter by fields are not displayed 10. Select the Reset button and verify the previously selected criteria is cleared |  | FC |  |  |  |  | FC
Milestone Tracker | 1. Login to iQ as a OC and select a facility 2. Select Trends > Data Volume on the left-hand menu 3. Verify the following are displayed for HL7 Message Submissioms: a. Filter icon b. Filter by: Year, Month, Current Month c. Search d. Reset 4. Verify when Time Frequency of 'Month' is selected, the Month dropdown displays all the months 5. Verify when Time Frequency of 'Quarterly' is selected, the Quarter dropdown displays 1, 2, 3, 4 6. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 7. Select the Month that will incorporate the messages that were imported 8. Ensure the correct number of messages are counted for the different Milestones for the Milestone Tracker 9. Select the frequency of 10-day Interval, month and the 10 day interval values that will incorporate the messages that were imported 10. Ensure the correct number of messages are counted for the different Milestones for the Milestone Tracker 11. Select the frequency of quarter and a quarter value that will not incorporate the messages that were imported 12. Ensure a message of "No Data Available For Selected Criteria" is displayed 13. Select the Filter icon and verify the filter by fields are not displayed 14. Select the Reset button and verify the previously selected criteria is cleared |  | OC |  |  |  |  | OC
| 1. Login to iQ as a FC 2. Select Trends > Data Volume on the left-hand menu 3. Verify the following are displayed for HL7 Message Submissioms: a. Filter icon b. Filter by: Year, Month, Current Month c. Search d. Reset 4. Verify when Time Frequency of 'Month' is selected, the Month dropdown displays all the months 5. Verify when Time Frequency of 'Quarterly' is selected, the Quarter dropdown displays 1, 2, 3, 4 6. Verify when Time Frequency of '10 Day Interval' is selected, the Month dropdown displays all the months; verify each Time Frequency of 'Month' that the '10 Day Interval' dropdown displays the correct 10 day intervals. 7. Select the Month that will incorporate the messages that were imported 8. Ensure the correct number of messages are counted for the different Milestones for the Milestone Tracker 9. Select the frequency of 10-day Interval, month and the 10 day interval values that will incorporate the messages that were imported 10. Ensure the correct number of messages are counted for the different Milestones for the Milestone Tracker 11. Select the frequency of quarter and a quarter value that will not incorporate the messages that were imported 12. Ensure a message of "No Data Available For Selected Criteria" is displayed 13. Select the Filter icon and verify the filter by fields are not displayed 14. Select the Reset button and verify the previously selected criteria is cleared |  | FC |  |  |  |  | FC